## Testing & Validation Plan
HealthConnect Project — Week 7 Testing & Validation Plan
What is being tested, by whom, and how it depends on other tracks' testing
Workstream | What Is Being Tested | Testing Method | Depends On | Owner | Target Completion
Project Management | Whether Week 6 integration decisions (DEC-02, DEC-04) hold up under real Phase 3/testing conditions | Cross-track validation of DEP-002 and DEP-004 at scale | Data Analytics, Generative AI Week 7 outputs | Project Manager | End of Week 7
Data Analytics | Accuracy and consistency of validated KPIs and the fallback patient-identifier approach at full Phase 3 scale | Recalculation against underlying data; segment consistency checks | Phase 3 data quality work | Data Analyst | Mid-Week 7
Data Science | Candidate model performance vs. Week 5 baseline; error analysis | Held-out test data; classification metrics; false positive/negative review | Data Analytics validated features | Data Scientist | Mid-Week 7
ML Engineering | Integrated pipeline reliability, input/output validation, error handling | Component and integration testing; invalid-input scenarios | Data Science candidate model | ML Engineer | Late Week 7
Generative AI | Assistant safety, consistency, and Knowledge Base compliance under an expanded, harder test set | Structured test scenarios incl. ambiguous/unsupported/escalation cases | None (self-contained, but PM validates result) | Generative AI Developer | Mid-Week 7

## Updated Timeline
HealthConnect Project — Updated Timeline (Week 7 Checkpoint)
Phase 3 validated and effectively complete; Phase 4 (Solution Design) now starting.
Major Phase | Key Activity | Milestone | Start Date | End Date | Status | Depends On
Phase 1 — Project Initiation (2026-08-31 to 2026-09-15) | • 1.1 Confirm business problem & central question |  | 2026-08-31 | 2026-09-01 | Complete | —
| • 1.2 Review data resources & confirm assumptions |  | 2026-08-31 | 2026-09-01 | Complete | —
| • 1.3 Develop Project Charter & obtain Sponsor sign-off |  | 2026-09-02 | 2026-09-10 | Complete | 1.1; 1.2
| • 1.4 Compile Stakeholder Register |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| • 1.5 Confirm resourcing |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| Milestone | Project Charter approved by Sponsor | 2026-09-15 | 2026-09-15 | Achieved
Phase 2 — Planning (2026-09-16 to 2026-10-02) | • 2.1 Develop Work Breakdown Structure |  | 2026-09-16 | 2026-09-18 | Complete | 1.4; 1.5
| • 2.2 Develop project schedule (activity durations & dependencies) |  | 2026-09-21 | 2026-09-23 | Complete | 2.1
| • 2.3 Build network diagram & critical path analysis |  | 2026-09-24 | 2026-09-25 | Complete | 2.2
| • 2.4 Conduct schedule risk analysis |  | 2026-09-28 | 2026-09-29 | Complete | 2.3
| • 2.5 Develop Resource Management Plan |  | 2026-09-16 | 2026-09-18 | Complete | 1.4; 1.5
| • 2.6 Develop Communication Plan |  | 2026-09-16 | 2026-09-17 | Complete | 1.4
| • 2.7 Develop Quality Management Plan |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| • 2.8 Develop cost baseline / Project Budget |  | 2026-09-24 | 2026-09-28 | Complete | 2.2
| • 2.9 Expand Risk Register & Dependency Register to full planning detail |  | 2026-09-30 | 2026-10-01 | Complete | 2.4
| • 2.10 Planning phase gate: baseline sign-off (scope, schedule, cost) |  | 2026-10-02 | 2026-10-02 | Complete | 2.4; 2.5; 2.6; 2.7; 2.8; 2.9
| Milestone | Planning phase gate: baseline sign-off (scope, schedule, cost) | 2026-10-02 | 2026-10-02 | Achieved
Phase 3 — Analysis & Data Preparation (2026-10-05 to 2026-10-14) | • 3.1 Data quality assessment & cleaning |  | 2026-10-05 | 2026-10-09 | Complete | 2.10
| • 3.2 Exploratory data analysis & KPI definition |  | 2026-10-05 | 2026-10-09 | Complete | 2.10
| • 3.3 Confirm/construct unified patient identifier |  | 2026-10-05 | 2026-10-09 | Complete | 2.10
| • 3.4 Define no-show prediction problem |  | 2026-10-12 | 2026-10-14 | Complete | 3.1; 3.2; 3.3
| Milestone | No-show prediction problem formally defined | 2026-10-14 | 2026-10-14 | Achieved — validated Week 7
Phase 4 — Solution Design (2026-10-15 to 2026-10-28) | • 4.1 Model design & validation approach |  | 2026-10-15 | 2026-10-20 | In Progress | 3.4
| • 4.2 Segmentation design |  | 2026-10-15 | 2026-10-20 | In Progress | 3.4
| • 4.3 ML system architecture & reproducibility design |  | 2026-10-21 | 2026-10-27 | In Progress | 4.1; 4.2
| • 4.4 GenAI assistant scope & safety boundaries |  | 2026-10-21 | 2026-10-27 | In Progress | 4.1; 4.2
| • 4.5 Dashboard/report design |  | 2026-10-21 | 2026-10-27 | In Progress | 4.1; 4.2
| • 4.6 Phase gate: design review & Sponsor go/no-go |  | 2026-10-28 | 2026-10-28 | In Progress | 4.3; 4.4; 4.5
| Milestone | Design approved at Phase Gate (Sponsor go/no-go) | 2026-10-28 | 2026-10-28 | Not due
Phase 5 — Model & Assistant Development (2026-10-29 to 2027-02-04) | • 5.1 Build & iteratively test no-show prediction model |  | 2026-10-29 | 2027-01-20 | Not Started | 4.6
| • 5.2 Build data integration / pipeline |  | 2026-10-29 | 2026-11-25 | Not Started | 4.6
| • 5.3 Build reproducible ML pipeline & version control |  | 2026-11-26 | 2027-01-20 | Not Started | 5.2
| • 5.4 Build GenAI assistant prototype |  | 2026-10-29 | 2027-02-03 | Not Started | 4.6
| • 5.5 Build dashboard/reporting |  | 2026-11-26 | 2027-01-13 | Not Started | 5.2
| • 5.6 Mid-development integration checkpoint |  | 2027-02-04 | 2027-02-04 | Not Started | 5.1; 5.3; 5.4; 5.5
| Milestone | Mid-development integration checkpoint | 2027-02-04 | 2027-02-04 | Not due
Phase 6 — Pilot Campaign (2027-02-05 to 2027-02-19) | • 6.1 Validate segments with clinic staff |  | 2027-02-05 | 2027-02-08 | Not Started | 5.6
| • 6.2 Train staff on dashboard & flagged-patient process |  | 2027-02-09 | 2027-02-11 | Not Started | 6.1
| • 6.3 Run pilot reminder/retention campaign |  | 2027-02-12 | 2027-02-18 | Not Started | 6.2
| • 6.4 Measure pilot results vs. control group |  | 2027-02-19 | 2027-02-19 | Not Started | 6.3
| Milestone | Pilot results measured against control group | 2027-02-19 | 2027-02-19 | Not due
Phase 7 — Testing, Deployment & Monitoring (2027-02-22 to 2027-03-10) | • 7.1 Model validation against test data & KPI targets |  | 2027-02-22 | 2027-02-24 | Not Started | 6.4
| • 7.2 Assistant safety & scope testing |  | 2027-02-22 | 2027-02-24 | Not Started | 6.4
| • 7.3 Production deployment |  | 2027-02-25 | 2027-03-03 | Not Started | 7.1; 7.2
| • 7.4 Establish monitoring & retraining schedule |  | 2027-03-04 | 2027-03-10 | Not Started | 7.3
| Milestone | Model and assistant live in production | 2027-03-10 | 2027-03-10 | Not due
Phase 8 — Operational Handover & Closure (2027-03-11 to 2027-03-17) | • 8.1 Train internal IT/Data team |  | 2027-03-11 | 2027-03-15 | Not Started | 7.4
| • 8.2 Final presentation & documentation handover |  | 2027-03-16 | 2027-03-16 | Not Started | 8.1
| • 8.3 Project closure & lessons learned |  | 2027-03-17 | 2027-03-17 | Not Started | 8.2
| Milestone | Operational handover complete; project closed | 2027-03-17 | 2027-03-17 | Not due

## Testing Activity Tracker
HealthConnect Project — Testing Activity Tracker (Week 7)
Cross-workstream testing activities, status, and dependencies between them
ID | Testing Activity | Workstream | Depends On | Status | Owner | Notes
TA-01 | Validate fallback patient-identifier approach at full Phase 3 data scale | Data Analytics / PM | — | Complete | Data Analyst / Project Manager | See Testing & Validation Record TR-01
TA-02 | Validate KPI calculations and dashboard values against underlying data | Data Analytics | — | Complete | Data Analyst | Feeds TA-01 and the Risk Register update
TA-03 | Test candidate no-show model on held-out data; compare to Week 5 baseline | Data Science | TA-02 (validated features) | In Progress | Data Scientist | Reported to PM for schedule tracking only
TA-04 | Test integrated ML pipeline input/output validation and error handling | ML Engineering | TA-03 (candidate model) | Not Started | ML Engineer | Blocked until model finalised
TA-05 | Test assistant against expanded scenario set (ambiguous, unsupported, escalation) | Generative AI / PM | — | Complete | Generative AI Developer / Project Manager | See Testing & Validation Record TR-02
TA-06 | Validate that Week 6 IT Lead capacity escalation (DEP-009) has a resourcing decision | IT / PM | — | Open | Project Manager | Still awaiting Sponsor decision — see Issue Log

## Integration & Issue Log
HealthConnect Project — Integration & Issue Log (Week 7)
Issues found during testing, with assigned owners and tracked status
ID | Issue | Found During | Tracks Affected | Severity | Status | Action Taken | Retest Result | Owner
ISS-05 | A small subset of records lack enough matching fields even for the fallback patient identifier | TA-01 (Data Analytics identifier validation) | Data Analytics, Data Engineering | Low | Resolved | Data Analytics quantified the affected subset and proposed an exclusion/handling rule | Retested — affected subset reduced to a negligible, documented level | Data Analyst
ISS-06 | Assistant gave inconsistent responses to ambiguous multi-part questions | TA-05 (Generative AI expanded testing) | Generative AI | Low | Resolved | Generative AI refined prompt handling for multi-part questions | Retested — consistency confirmed across the expanded scenario set | Generative AI Developer
ISS-07 | IT Lead capacity conflict still unresolved; no Sponsor decision yet | TA-06 (dependency validation) | IT, Data Engineering | Medium | Open | Re-escalated to Sponsor with a specific deadline requested | Not yet retested — pending Sponsor response | Project Manager
ISS-08 | Data Science model comparison still in progress; model interface (DEP-011) remains undefined | TA-03 (model testing, in progress) | Data Science, ML Engineering | Low | Open | Monitoring; no action needed until Data Science completes comparison | N/A — not yet due | Data Scientist / ML Engineer

## Updated Risk Register
HealthConnect Project — Updated Risk Register (Week 7 Checkpoint)
Risk Score = Likelihood value × Impact value (see scale, cols K:L). Statuses updated following Week 7 testing.
ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner | Status | Scale
R1 | Data quality issues in the appointment dataset (missing, inconsistent, or unclear fields) | Data | Low | Medium | 2 | Validated at full Phase 3 scale in Week 7 (TA-01); residual subset issue resolved via exclusion rule (ISS-05) | Data Engineer | Validated — confirmed manageable at scale | Level | Value
R2 | No-show prediction model accuracy falls below the 75% target | Model | Medium | High | 6 | Testing under way against held-out data (TA-03); result pending | Data Scientist | Testing in progress | Low | 1
R3 | Low staff adoption of at-risk patient flags and reminder recommendations | Adoption | Medium | Medium | 4 | Early staff involvement in segment validation and structured training planned for Phase 6 | Project Manager | Open | Medium | 2
R4 | Generative AI assistant produces out-of-scope or unsafe responses (e.g., clinical advice) | Safety / Compliance | Low | High | 3 | Retested in Week 7 against an expanded, harder scenario set (TA-05); minor consistency issue found and resolved (ISS-06) | Generative AI Developer | Validated — confirmed under harder testing | High | 3
R5 | Insufficient internal capacity at HealthConnect to sustain monitoring and retraining after handover | Operational | Medium | High | 6 | Confirm internal team availability ahead of Phase 8 | Project Manager | Open
R6 | Data privacy / POPIA compliance exposure given health-related patient data | Compliance | Medium | High | 6 | Compliance Officer sign-off at each phase gate | Compliance Officer | Monitoring
R7 | Schedule pressure from the December office closure falling within the project timeline | Schedule | High | Medium | 6 | December fully excluded from the active schedule; work resumes after the recess with buffer | Project Manager | Open
R8 | Dependency on third-party LLM/API availability, rate limits, or cost for the assistant | Technical / Vendor | Low | Medium | 2 | Early API access testing; fallback/offline model option identified | IT Lead | Open
R9 | Scope creep beyond the agreed prototype/pilot boundary into full production rollout without sign-off | Scope | Low | High | 3 | Reinforce Scope Statement; Sponsor sign-off required through change control for any scope change | Project Manager | Open
R10 | Budget overrun beyond the approved contingency due to unforeseen integration complexity | Financial | Low | Medium | 2 | Weekly budget tracking; contingency draws logged and approved per the authority matrix | Project Manager | Open
R12 | IT Lead has a capacity conflict with commitments outside the project, risking delays to identifier resolution and deployment support | Resource | Medium | Medium | 4 | Re-escalated to Sponsor this week with a specific deadline requested (ISS-07) | Project Manager | Escalated — unresolved
R14 | Data Science model interface not yet finalised, which may delay ML Engineering's pipeline integration scoping | Technical / Integration | Low | Low | 1 | Monitoring; not yet a blocker (ISS-08) | Data Scientist / ML Engineer | Open
R15 | A small subset of appointment records cannot be matched even with the fallback identifier | Data | Low | Low | 1 | Exclusion rule applied and validated in Week 7 (ISS-05) | Data Engineer | Closed — resolved and retested
R16 | Assistant inconsistency on ambiguous multi-part questions | Safety / Reliability | Low | Low | 1 | Prompt refinement applied and validated in Week 7 (ISS-06) | Generative AI Developer | Closed — resolved and retested

## Updated Dependency Register
HealthConnect Project — Updated Dependency Register (Week 7 Checkpoint)
Tracked separately from the Risk Register
Dependency ID | Dependency / Description | Dependent Activity/Task | Dependency Type | Source / Owner | Required By | Status | Impact if Delayed | Criticality | Mitigation / Action | Responsible Person | Notes
DEP-002 | A common (or derivable) patient identifier confirmed across scheduling and reminder records | 3.3 Confirm/construct unified patient identifier | Technical | Data Engineer | 2026-10-09 | Validated | Data integration would require rework | Critical | Fallback linking key tested at full Phase 3 scale in Week 7 (TA-01) | Data Engineer | Upgraded from Mitigated to Validated following retest
DEP-004 | Finalised, Sponsor-approved Clinic Knowledge Base scope for the patient information assistant | 4.4 GenAI assistant scope & safety boundaries | Content / Governance | Generative AI Developer | 2026-10-27 | Validated | Assistant scope could remain unreliable under real use | High | Retested against an expanded scenario set in Week 7 (TA-05) | Generative AI Developer | Upgraded from Complete to Validated following retest
DEP-009 | Confirmed dedicated IT Lead capacity, prioritised against the IT Lead's other commitments | 3.3 Confirm/construct unified patient identifier; ongoing IT support | Resource | IT Lead's Line Manager | 2026-10-09 | At Risk | Identifier resolution and later deployment support both delayed | Medium | Re-escalated to Sponsor this week with a specific deadline requested | Project Manager | Unresolved for a second consecutive week
DEP-011 | Data Science candidate model interface (input/output format) needed before pipeline integration work can begin | 5.3 Build reproducible ML pipeline & version control | Technical | Data Scientist | TBD — Phase 5 | Not Started | ML Engineering integration work blocked at the start of Phase 5 | Medium | Monitoring Data Science's model comparison progress | Data Scientist / ML Engineer | Not yet due; not a current blocker

## Decision Log
HealthConnect Project — Decision Log (Week 7)
Major project decisions made during testing and refinement
ID | Decision | Rationale | Made By | Date | Impact
DEC-05 | Apply a documented exclusion rule for the small subset of records the fallback identifier cannot match | Testing at full Phase 3 scale (TA-01) found a narrow residual gap not visible in the Week 6 sample validation | Project Manager, with Data Analyst | 2026-10-09 | DEP-002 upgraded to Validated; Phase 3 data preparation can close cleanly
DEC-06 | Accept the Generative AI track's Week 7 retest results as confirming R4's downgrade | Expanded, harder test set found only one minor consistency issue, which was resolved and retested | Project Manager | 2026-10-27 | DEP-004 upgraded to Validated; R4 stays at Low likelihood rather than reopening
DEC-07 | Re-escalate the IT Lead capacity conflict to the Sponsor with a specific response deadline | Second consecutive week without a resourcing decision; risk to Phase 7 deployment support is growing | Project Manager | 2026-10-09 | ISS-07 tracked as open with an explicit deadline rather than left indefinitely pending

## Coordination Record
HealthConnect Project — Cross-Track Coordination Record (Week 7)
Log of coordination touchpoints between tracks this week
Date | Tracks Involved | Topic | Outcome | Evidence | Follow-up Owner
2026-10-09 | Project Management, Data Analytics | Validating the fallback patient identifier at full Phase 3 scale | Residual matching gap found and resolved via an exclusion rule; DEP-002 upgraded to Validated | Testing & Validation Record TR-01; Decision Log DEC-05 | Project Manager
2026-10-27 | Project Management, Generative AI | Retesting assistant safety/consistency against an expanded scenario set | Minor consistency issue found and resolved; DEP-004 upgraded to Validated | Testing & Validation Record TR-02; Decision Log DEC-06 | Project Manager
2026-10-09 | Project Management, IT | Second check-in on the unresolved IT Lead capacity conflict | Still unresolved; re-escalated to Sponsor with a specific deadline | Decision Log DEC-07; Issue Log ISS-07 | Sponsor
2026-10-28 | Project Management, Data Science | Status check on model comparison progress ahead of the ML Engineering handoff | In progress, on track; model interface (DEP-011) remains a monitored, non-blocking dependency | Testing Activity Tracker TA-03; Issue Log ISS-08 | Data Scientist

## Testing & Validation Record
HealthConnect Project — Testing, Refinement & Validation Record
Format per assignment Section 12. Two cross-track entries (TR-01, TR-02) plus one PM-internal entry (TR-03).
ID | Component Tested | Testing Objective | Test/Scenario | Expected Result | Actual Result | Pass/Fail | Issue Identified | Action Taken | Retest Result | Collaborating Track | Evidence
TR-01 | Fallback patient-identifier linking key (adopted Week 6, DEC-02) | Determine whether the fallback identifier holds at full Phase 3 data scale, not just the Week 6 sample | Apply the fallback identifier across the full Phase 3 dataset extract | Identifier produces a usable, consistent patient-level match for effectively all records | Worked for the large majority of records; a small subset lacked enough matching fields even for the fallback | Partial Pass | Small subset of records unmatched (ISS-05) | Data Analytics quantified the subset and proposed a documented exclusion rule | Retested — subset reduced to a negligible, documented level; approach confirmed workable | Data Analytics | Updated Risk Register (R1, R15); Dependency Register (DEP-002); Decision Log DEC-05
TR-02 | Patient information assistant Knowledge-Base safety boundary (closed Week 6, DEP-004) | Determine whether the assistant remains safe and consistent under a wider, harder test set than Week 6 | Run the expanded Week 7 scenario set: ambiguous, unsupported, escalation, and multi-part questions | Assistant stays within the Knowledge Base, escalates correctly, and responds consistently across all scenario types | Performed well on most new scenarios; inconsistent handling found on ambiguous multi-part questions | Pass with Minor Finding | Inconsistent responses to ambiguous multi-part questions (ISS-06) | Generative AI refined prompt handling for multi-part questions | Retested — consistency confirmed across the expanded scenario set | Generative AI | Updated Risk Register (R4, R16); Dependency Register (DEP-004); Decision Log DEC-06
TR-03 | IT Lead resourcing dependency (escalated Week 6, DEP-009) | Determine whether the Week 6 escalation produced a resourcing decision | Follow up directly with the Sponsor on the outstanding decision | A resourcing decision is made, resolving the capacity conflict | No decision yet; conflict remains unresolved for a second consecutive week | Fail | Escalation did not produce a timely decision (ISS-07) | Re-escalated with a specific response deadline attached | Not yet retested — pending Sponsor response | IT | Decision Log DEC-07; Issue Log ISS-07

## Week 8 Readiness
HealthConnect Project — Week 8 Readiness Assessment
Assessment of what is ready for Final Integration & Presentation vs. what remains outstanding
Area | Readiness | Basis | Outstanding Action Before Week 8
Data quality / patient identifier (DEP-002) | Ready | Validated at full Phase 3 scale (TR-01); exclusion rule documented and retested | None
Generative AI assistant safety scope (DEP-004) | Ready | Retested against expanded scenario set (TR-02); minor issue resolved | None
No-show prediction model | Not yet ready | Testing in progress (TA-03); result not yet available | Complete model testing and report result to PM
ML pipeline integration | Not yet ready | Blocked on model finalisation (TA-04) | Cannot start until Data Science testing completes
IT Lead resourcing / deployment support | At risk | Escalated twice without resolution (DEP-009, ISS-07) | Sponsor decision required before Phase 7 deployment planning
Overall schedule baseline | On track | No date changes this week; Phase 3 closed as planned | None
Overall project alignment with HealthConnect objective | On track | All Week 7 activity traced back to reducing no-shows / improving patient support (see Part 2, task 18 in the report) | None