## Updated Timeline
HealthConnect Project — Updated Timeline (Week 6 Checkpoint)
Planning baseline signed off this week; Phase 3 now formally In Progress.
Major Phase | Key Activity | Milestone | Start Date | End Date | Status | Depends On
Phase 1 — Project Initiation (2026-08-31 to 2026-09-15) | • 1.1 Confirm business problem & central question |  | 2026-08-31 | 2026-09-01 | Complete | —
| • 1.2 Review data resources & confirm assumptions |  | 2026-08-31 | 2026-09-01 | Complete | —
| • 1.3 Develop Project Charter & obtain Sponsor sign-off |  | 2026-09-02 | 2026-09-10 | Complete | 1.1; 1.2
| • 1.4 Compile Stakeholder Register |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| • 1.5 Confirm resourcing |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| Milestone | Project Charter approved by Sponsor | 2026-09-15 | 2026-09-15 | Achieved
Phase 2 — Planning (2026-09-16 to 2026-10-02) | • 2.1 Develop Work Breakdown Structure |  | 2026-09-16 | 2026-09-18 | Complete | 1.4; 1.5
| • 2.2 Develop project schedule (activity durations & dependencies) |  | 2026-09-21 | 2026-09-23 | Complete | 2.1
| • 2.3 Build network diagram & critical path analysis |  | 2026-09-24 | 2026-09-25 | Complete | 2.2
| • 2.4 Conduct schedule risk analysis |  | 2026-09-28 | 2026-09-29 | Complete | 2.3
| • 2.5 Develop Resource Management Plan |  | 2026-09-16 | 2026-09-18 | Complete | 1.4; 1.5
| • 2.6 Develop Communication Plan |  | 2026-09-16 | 2026-09-17 | Complete | 1.4
| • 2.7 Develop Quality Management Plan |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| • 2.8 Develop cost baseline / Project Budget |  | 2026-09-24 | 2026-09-28 | Complete | 2.2
| • 2.9 Expand Risk Register & Dependency Register to full planning detail |  | 2026-09-30 | 2026-10-01 | Complete | 2.4
| • 2.10 Planning phase gate: baseline sign-off (scope, schedule, cost) |  | 2026-10-02 | 2026-10-02 | Complete | 2.4; 2.5; 2.6; 2.7; 2.8; 2.9
| Milestone | Planning phase gate: baseline sign-off (scope, schedule, cost) | 2026-10-02 | 2026-10-02 | Achieved (signed off Week 6)
Phase 3 — Analysis & Data Preparation (2026-10-05 to 2026-10-14) | • 3.1 Data quality assessment & cleaning |  | 2026-10-05 | 2026-10-09 | In Progress | 2.10
| • 3.2 Exploratory data analysis & KPI definition |  | 2026-10-05 | 2026-10-09 | In Progress | 2.10
| • 3.3 Confirm/construct unified patient identifier |  | 2026-10-05 | 2026-10-09 | In Progress | 2.10
| • 3.4 Define no-show prediction problem |  | 2026-10-12 | 2026-10-14 | In Progress | 3.1; 3.2; 3.3
| Milestone | No-show prediction problem formally defined | 2026-10-14 | 2026-10-14 | Not due
Phase 4 — Solution Design (2026-10-15 to 2026-10-28) | • 4.1 Model design & validation approach |  | 2026-10-15 | 2026-10-20 | Not Started | 3.4
| • 4.2 Segmentation design |  | 2026-10-15 | 2026-10-20 | Not Started | 3.4
| • 4.3 ML system architecture & reproducibility design |  | 2026-10-21 | 2026-10-27 | Not Started | 4.1; 4.2
| • 4.4 GenAI assistant scope & safety boundaries |  | 2026-10-21 | 2026-10-27 | Not Started | 4.1; 4.2
| • 4.5 Dashboard/report design |  | 2026-10-21 | 2026-10-27 | Not Started | 4.1; 4.2
| • 4.6 Phase gate: design review & Sponsor go/no-go |  | 2026-10-28 | 2026-10-28 | Not Started | 4.3; 4.4; 4.5
| Milestone | Design approved at Phase Gate (Sponsor go/no-go) | 2026-10-28 | 2026-10-28 | Not due
Phase 5 — Model & Assistant Development (2026-10-29 to 2027-02-04) | • 5.1 Build & iteratively test no-show prediction model |  | 2026-10-29 | 2027-01-20 | Not Started | 4.6
| • 5.2 Build data integration / pipeline |  | 2026-10-29 | 2026-11-25 | Not Started | 4.6
| • 5.3 Build reproducible ML pipeline & version control |  | 2026-11-26 | 2027-01-20 | Not Started | 5.2
| • 5.4 Build GenAI assistant prototype |  | 2026-10-29 | 2027-02-03 | Not Started | 4.6
| • 5.5 Build dashboard/reporting |  | 2026-11-26 | 2027-01-13 | Not Started | 5.2
| • 5.6 Mid-development integration checkpoint |  | 2027-02-04 | 2027-02-04 | Not Started | 5.1; 5.3; 5.4; 5.5
| Milestone | Mid-development integration checkpoint | 2027-02-04 | 2027-02-04 | Not due
Phase 6 — Pilot Campaign (2027-02-05 to 2027-02-19) | • 6.1 Validate segments with clinic staff |  | 2027-02-05 | 2027-02-08 | Not Started | 5.6
| • 6.2 Train staff on dashboard & flagged-patient process |  | 2027-02-09 | 2027-02-11 | Not Started | 6.1
| • 6.3 Run pilot reminder/retention campaign |  | 2027-02-12 | 2027-02-18 | Not Started | 6.2
| • 6.4 Measure pilot results vs. control group |  | 2027-02-19 | 2027-02-19 | Not Started | 6.3
| Milestone | Pilot results measured against control group | 2027-02-19 | 2027-02-19 | Not due
Phase 7 — Testing, Deployment & Monitoring (2027-02-22 to 2027-03-10) | • 7.1 Model validation against test data & KPI targets |  | 2027-02-22 | 2027-02-24 | Not Started | 6.4
| • 7.2 Assistant safety & scope testing |  | 2027-02-22 | 2027-02-24 | Not Started | 6.4
| • 7.3 Production deployment |  | 2027-02-25 | 2027-03-03 | Not Started | 7.1; 7.2
| • 7.4 Establish monitoring & retraining schedule |  | 2027-03-04 | 2027-03-10 | Not Started | 7.3
| Milestone | Model and assistant live in production | 2027-03-10 | 2027-03-10 | Not due
Phase 8 — Operational Handover & Closure (2027-03-11 to 2027-03-17) | • 8.1 Train internal IT/Data team |  | 2027-03-11 | 2027-03-15 | Not Started | 7.4
| • 8.2 Final presentation & documentation handover |  | 2027-03-16 | 2027-03-16 | Not Started | 8.1
| • 8.3 Project closure & lessons learned |  | 2027-03-17 | 2027-03-17 | Not Started | 8.2
| Milestone | Operational handover complete; project closed | 2027-03-17 | 2027-03-17 | Not due

## Integration-Dependency Register
HealthConnect Project — Integration & Dependency Register (Week 6)
Cross-workstream dependencies, extended from the Planning-stage Dependency Register with integration-specific items.
ID | Dependency / Description | From Track | To Track | Type | Required By | Status | Impact if Delayed | Criticality | Mitigation / Action | Responsible Person | Notes
DEP-002 | A common (or derivable) patient identifier confirmed across scheduling and reminder records | Data Engineering | Data Science / PM | Technical | 2026-10-09 | Mitigated | Data integration required rework if unresolved | Critical | Fallback linking key confirmed workable during Week 6 validation | Data Engineer | Downgraded from At Risk following Data Analytics validation
DEP-004 | Finalised, Sponsor-approved Clinic Knowledge Base scope for the patient information assistant | Generative AI | Project Management | Content / Governance | 2026-10-27 | Complete | Assistant scope would remain undefined | High | GenAI track delivered safety/scope testing evidence in Week 6; closed | Generative AI Developer | Closed via Week 6 cross-track integration
DEP-009 | Confirmed dedicated IT Lead capacity, prioritised against the IT Lead's other commitments | IT | Data Engineering / PM | Resource | 2026-10-09 | At Risk | Identifier resolution and later deployment support both delayed | Medium | Escalated to Sponsor for a resourcing decision this week | Project Manager | Unresolved — carried from Week 5
DEP-010 | Sponsor sign-off on the Planning-stage baseline (scope, schedule, cost) | Project Management | Sponsor | Governance | 2026-10-02 | Complete | Phase 3 could not formally start without an approved baseline | Critical | Signed off at the start of Week 6 | Project Manager | Closed — Phase 3 now In Progress
DEP-011 | Data Science candidate model interface (input/output format) needed before pipeline integration work can begin | Data Science | ML Engineering | Technical | TBD — Phase 5 | Not Started | ML Engineering integration work blocked at the start of Phase 5 | Medium | To be finalised once Data Science completes model comparison in a later cycle | Data Scientist / ML Engineer | New — identified during Week 6 integration mapping
DEP-012 | Validated Data Analytics findings on data quality severity needed to confirm the Phase 3 effort estimate | Data Analytics | Project Management | Analytical | 2026-10-09 | Complete | Phase 3 effort estimate would remain unvalidated | Medium | Findings received and incorporated into the Risk Register this week | Project Manager | Closed via Week 6 cross-track integration

## Integration Issue Log
HealthConnect Project — Integration Issue Log (Week 6)
Issues discovered while connecting workstream outputs
ID | Issue | Tracks Affected | Severity | Status | Resolution / Action | Owner | Date Raised
ISS-01 | No clean shared patient identifier exists across scheduling and reminder records | Data Engineering, Data Science | High | Resolved | Fallback linking key approach validated and adopted | Data Engineer | 2026-10-09
ISS-02 | Data Science model interface format not yet defined, so ML Engineering cannot scope pipeline integration work | Data Science, ML Engineering | Medium | Open | Flagged for resolution once Data Science completes model comparison | Data Scientist / ML Engineer | 2026-10-28
ISS-03 | IT Lead capacity conflict not yet resolved, risking both current and future integration work | IT, Data Engineering | Medium | Open | Escalated to Sponsor this week; awaiting resourcing decision | Project Manager | 2026-10-09
ISS-04 | Assistant safety/scope testing evidence needed a common format before Project Management could close the Knowledge Base dependency | Generative AI, Project Management | Low | Resolved | Evidence reviewed and accepted against the Quality Management Plan's criteria | Generative AI Developer | 2026-10-27

## Decision Log
HealthConnect Project — Decision Log (Week 6)
Major project decisions made this week
ID | Decision | Rationale | Made By | Date | Impact
DEC-01 | Adopt the ~24-week CPM-derived schedule as the formal project baseline | Compression back to 20 weeks would consume float from Phase 5, which already has the least buffer in the project | Sponsor (on PM recommendation) | 2026-10-02 | Planning phase gate (2.10) closed; Phase 3 formally started
DEC-02 | Adopt a fallback patient-identifier linking key rather than waiting for a clean shared identifier | Week 6 validation confirmed no clean shared identifier exists across systems | Project Manager, with Data Engineer | 2026-10-09 | Removes ambiguity blocking Phase 3 data preparation work
DEC-03 | Escalate the IT Lead capacity conflict to the Sponsor rather than continuing to monitor informally | Two consecutive weeks without resolution; risk to both current and future deployment work | Project Manager | 2026-10-09 | Awaiting Sponsor resourcing decision; tracked as DEP-009
DEC-04 | Accept the Generative AI track's Week 6 safety/scope testing evidence as sufficient to close the Knowledge Base scope dependency | Evidence met the criteria set out in the Quality Management Plan | Project Manager | 2026-10-27 | DEP-004 closed; assistant design work can proceed without an open governance item

## Updated Risk Register
HealthConnect Project — Updated Risk Register (Week 6 Checkpoint)
Risk Score = Likelihood value × Impact value (see scale, cols K:L). Statuses updated following Week 6 integration activity.
ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner | Status | Scale
R1 | Data quality issues in the appointment dataset (missing, inconsistent, or unclear fields) | Data | Medium | High | 6 | Validated during Week 6: manageable with the planned Phase 3 cleaning effort | Data Engineer | Validated — downgraded from High | Level | Value
R2 | No-show prediction model accuracy falls below the 75% target | Model | Medium | High | 6 | Iterative build-test cycles (5.1); feature engineering review if early accuracy lags | Data Scientist | Open | Low | 1
R3 | Low staff adoption of at-risk patient flags and reminder recommendations | Adoption | Medium | Medium | 4 | Early staff involvement in segment validation (6.1) and structured training (6.2) | Project Manager | Open | Medium | 2
R4 | Generative AI assistant produces out-of-scope or unsafe responses (e.g., clinical advice) | Safety / Compliance | Low | High | 3 | Week 6 safety/scope testing evidence reviewed and accepted; DEP-004 closed | Generative AI Developer | Reduced — likelihood downgraded from Medium | High | 3
R5 | Insufficient internal capacity at HealthConnect to sustain monitoring and retraining after handover | Operational | Medium | High | 6 | Confirm internal team availability early (DEP-008); structured handover training (8.1) | Project Manager | Open
R6 | Data privacy / POPIA compliance exposure given health-related patient data | Compliance | Medium | High | 6 | Compliance Officer sign-off at each phase gate; consent status confirmed early (DEP-003) | Compliance Officer | Monitoring
R7 | Schedule pressure from the December office closure falling within the project timeline | Schedule | High | Medium | 6 | December fully excluded from the active schedule; work resumes after the recess with buffer | Project Manager | Open
R8 | Dependency on third-party LLM/API availability, rate limits, or cost for the assistant | Technical / Vendor | Low | Medium | 2 | Early API access testing (5.4); fallback/offline model option identified | IT Lead | Open
R9 | Scope creep beyond the agreed prototype/pilot boundary into full production rollout without sign-off | Scope | Low | High | 3 | Reinforce Scope Statement; Sponsor sign-off required through change control for any scope change | Project Manager | Open
R10 | Budget overrun beyond the approved contingency due to unforeseen integration complexity | Financial | Low | Medium | 2 | Weekly budget tracking (9.2); contingency draws logged and approved per the authority matrix | Project Manager | Open
R11 | Initial data quality findings indicate more missing/inconsistent values than assumed at Charter stage | Data | Low | Medium | 2 | Resolved into R1 following Week 6 validation; Phase 3 effort estimate confirmed adequate | Project Manager | Closed — merged into R1
R12 | IT Lead has a capacity conflict with commitments outside the project, risking delays to identifier resolution and deployment support | Resource | Medium | Medium | 4 | Escalated to Sponsor this week (DEC-03); awaiting resourcing decision | Project Manager | Escalated
R13 | Formal Planning-stage CPM analysis showed the realistic project duration is ~24 weeks, not the originally assumed 20 | Schedule | Low | Medium | 2 | Sponsor accepted the 24-week baseline at the Planning phase gate (DEC-01) | Project Manager | Closed — baseline accepted
R14 | Data Science model interface not yet finalised, which may delay ML Engineering's pipeline integration scoping | Technical / Integration | Low | Low | 1 | Logged proactively during Week 6 integration mapping; to be resolved once model comparison completes | Data Scientist / ML Engineer | New — identified Week 6

## Coordination Record
HealthConnect Project — Cross-Track Coordination Record (Week 6)
Log of coordination touchpoints between tracks this week
Date | Tracks Involved | Topic | Outcome | Evidence | Follow-up Owner
2026-10-05 | Project Management, Data Analytics, Data Science | Validation of Week 5 data-quality concerns (R1/R11) | Findings confirmed the issue is real but manageable; R1 downgraded, R11 closed into R1 | Updated Risk Register; Decision Log DEC-02 | Project Manager
2026-10-27 | Project Management, Generative AI | Review of Week 6 safety/scope testing evidence against DEP-004 | Evidence accepted; Knowledge Base scope dependency formally closed | Integration/Dependency Register DEP-004; Decision Log DEC-04 | Project Manager
2026-10-09 | Project Management, IT | IT Lead capacity conflict (R12/DEP-009) status check | Unresolved; escalated to Sponsor for a resourcing decision | Decision Log DEC-03; Integration Issue Log ISS-03 | Sponsor
2026-10-28 | Project Management, Data Science, ML Engineering | Early scoping of the model-to-pipeline integration point ahead of Phase 5 | Interface format not yet available; logged as a forward-looking dependency rather than a blocker today | Integration/Dependency Register DEP-011; Issue Log ISS-02 | Data Scientist / ML Engineer