## Network Diagram
HealthConnect Project — Network Diagram (AON / CPM) Zoom in
Red border = Critical Path (zero float) ¦ Blue border = Non-critical (has float). Scroll right for later phases.
Full-resolution source image also provided separately as HealthConnect_Network_Diagram.png for printing/zooming.

## Project Schedule
HealthConnect Project - Schedule
Duration in working days. Predecessors shown as “# – Code – Name”- no lookup needed.
# | Code | Activity Name | Phase | Duration (days) | Predecessor(s) | Owner | Planned Dates
1 | 1.1 | Confirm business problem & central question | Phase 1- Project Initiation | 2 | — (project start) | Project Manager | 2026-08-31 → 2026-09-01
2 | 1.2 | Review data resources & confirm assumptions | Phase 1- Project Initiation | 2 | — (project start) | Project Manager | 2026-08-31 → 2026-09-01
3 | 1.3 | Develop Project Charter & obtain Sponsor sign-off | Phase 1- Project Initiation | 7 | 1 – 1.1 Confirm business problem & central question; 2 – 1.2 Review data resources & confirm assumptions | Project Manager | 2026-09-02 → 2026-09-10
4 | 1.4 | Compile Stakeholder Register | Phase 1- Project Initiation | 3 | 3 – 1.3 Develop Project Charter & obtain Sponsor sign-off | Project Manager | 2026-09-11 → 2026-09-15
5 | 1.5 | Confirm resourcing | Phase 1- Project Initiation | 3 | 3 – 1.3 Develop Project Charter & obtain Sponsor sign-off | Project Manager | 2026-09-11 → 2026-09-15
6 | 2.1 | Develop Work Breakdown Structure | Phase 2- Planning | 3 | 4 – 1.4 Compile Stakeholder Register; 5 – 1.5 Confirm resourcing | Project Manager | 2026-09-16 → 2026-09-18
7 | 2.2 | Develop project schedule (activity durations & dependencies) | Phase 2- Planning | 3 | 6 – 2.1 Develop Work Breakdown Structure | Project Manager | 2026-09-21 → 2026-09-23
8 | 2.3 | Build network diagram & critical path analysis | Phase 2- Planning | 2 | 7 – 2.2 Develop project schedule (activity durations & dependencies) | Project Manager | 2026-09-24 → 2026-09-25
9 | 2.4 | Conduct schedule risk analysis | Phase 2- Planning | 2 | 8 – 2.3 Build network diagram & critical path analysis | Project Manager | 2026-09-28 → 2026-09-29
10 | 2.5 | Develop Resource Management Plan | Phase 2- Planning | 3 | 4 – 1.4 Compile Stakeholder Register; 5 – 1.5 Confirm resourcing | Project Manager | 2026-09-16 → 2026-09-18
11 | 2.6 | Develop Communication Plan | Phase 2- Planning | 2 | 4 – 1.4 Compile Stakeholder Register | Project Manager | 2026-09-16 → 2026-09-17
12 | 2.7 | Develop Quality Management Plan | Phase 2- Planning | 3 | 3 – 1.3 Develop Project Charter & obtain Sponsor sign-off | Project Manager | 2026-09-11 → 2026-09-15
13 | 2.8 | Develop cost baseline / Project Budget | Phase 2- Planning | 3 | 7 – 2.2 Develop project schedule (activity durations & dependencies) | Project Manager | 2026-09-24 → 2026-09-28
14 | 2.9 | Expand Risk Register & Dependency Register to full planning detail | Phase 2- Planning | 2 | 9 – 2.4 Conduct schedule risk analysis | Project Manager | 2026-09-30 → 2026-10-01
15 | 2.10 | Planning phase gate: baseline sign-off (scope, schedule, cost) | Phase 2- Planning | 1 | 9 – 2.4 Conduct schedule risk analysis; 10 – 2.5 Develop Resource Management Plan; 11 – 2.6 Develop Communication Plan; 12 – 2.7 Develop Quality Management Plan; 13 – 2.8 Develop cost baseline / Project Budget; 14 – 2.9 Expand Risk Register & Dependency Register to full planning detail | Project Manager / Sponsor | 2026-10-02 → 2026-10-02
16 | 3.1 | Data quality assessment & cleaning | Phase 3- Analysis & Data Preparation | 5 | 15 – 2.10 Planning phase gate: baseline sign-off (scope, schedule, cost) | Data Engineer | 2026-10-05 → 2026-10-09
17 | 3.2 | Exploratory data analysis & KPI definition | Phase 3- Analysis & Data Preparation | 5 | 15 – 2.10 Planning phase gate: baseline sign-off (scope, schedule, cost) | Data Scientist | 2026-10-05 → 2026-10-09
18 | 3.3 | Confirm/construct unified patient identifier | Phase 3- Analysis & Data Preparation | 5 | 15 – 2.10 Planning phase gate: baseline sign-off (scope, schedule, cost) | Data Engineer | 2026-10-05 → 2026-10-09
19 | 3.4 | Define no-show prediction problem | Phase 3- Analysis & Data Preparation | 3 | 16 – 3.1 Data quality assessment & cleaning; 17 – 3.2 Exploratory data analysis & KPI definition; 18 – 3.3 Confirm/construct unified patient identifier | Data Scientist | 2026-10-12 → 2026-10-14
20 | 4.1 | Model design & validation approach | Phase 4- Solution Design | 4 | 19 – 3.4 Define no-show prediction problem | Data Scientist | 2026-10-15 → 2026-10-20
21 | 4.2 | Segmentation design | Phase 4- Solution Design | 4 | 19 – 3.4 Define no-show prediction problem | Data Scientist | 2026-10-15 → 2026-10-20
22 | 4.3 | ML system architecture & reproducibility design | Phase 4- Solution Design | 5 | 20 – 4.1 Model design & validation approach; 21 – 4.2 Segmentation design | ML Engineer | 2026-10-21 → 2026-10-27
23 | 4.4 | GenAI assistant scope & safety boundaries | Phase 4- Solution Design | 5 | 20 – 4.1 Model design & validation approach; 21 – 4.2 Segmentation design | Generative AI Developer | 2026-10-21 → 2026-10-27
24 | 4.5 | Dashboard/report design | Phase 4- Solution Design | 5 | 20 – 4.1 Model design & validation approach; 21 – 4.2 Segmentation design | Data Engineer | 2026-10-21 → 2026-10-27
25 | 4.6 | Phase gate: design review & Sponsor go/no-go | Phase 4- Solution Design | 1 | 22 – 4.3 ML system architecture & reproducibility design; 23 – 4.4 GenAI assistant scope & safety boundaries; 24 – 4.5 Dashboard/report design | Project Manager / Sponsor | 2026-10-28 → 2026-10-28
26 | 5.1 | Build & iteratively test no-show prediction model | Phase 5- Model & Assistant Development | 35 | 25 – 4.6 Phase gate: design review & Sponsor go/no-go | Data Scientist | 2026-10-29 → 2027-01-20
27 | 5.2 | Build data integration / pipeline | Phase 5- Model & Assistant Development | 20 | 25 – 4.6 Phase gate: design review & Sponsor go/no-go | Data Engineer | 2026-10-29 → 2026-11-25
28 | 5.3 | Build reproducible ML pipeline & version control | Phase 5- Model & Assistant Development | 15 | 27 – 5.2 Build data integration / pipeline | ML Engineer | 2026-11-26 → 2027-01-20
29 | 5.4 | Build GenAI assistant prototype | Phase 5- Model & Assistant Development | 45 | 25 – 4.6 Phase gate: design review & Sponsor go/no-go | Generative AI Developer | 2026-10-29 → 2027-02-03
30 | 5.5 | Build dashboard/reporting | Phase 5- Model & Assistant Development | 10 | 27 – 5.2 Build data integration / pipeline | Data Engineer | 2026-11-26 → 2027-01-13
31 | 5.6 | Mid-development integration checkpoint | Phase 5- Model & Assistant Development | 1 | 26 – 5.1 Build & iteratively test no-show prediction model; 28 – 5.3 Build reproducible ML pipeline & version control; 29 – 5.4 Build GenAI assistant prototype; 30 – 5.5 Build dashboard/reporting | Project Manager | 2027-02-04 → 2027-02-04
32 | 6.1 | Validate segments with clinic staff | Phase 6- Pilot Campaign | 2 | 31 – 5.6 Mid-development integration checkpoint | Clinic Admin & Clinical Staff | 2027-02-05 → 2027-02-08
33 | 6.2 | Train staff on dashboard & flagged-patient process | Phase 6- Pilot Campaign | 3 | 32 – 6.1 Validate segments with clinic staff | Project Manager | 2027-02-09 → 2027-02-11
34 | 6.3 | Run pilot reminder/retention campaign | Phase 6- Pilot Campaign | 5 | 33 – 6.2 Train staff on dashboard & flagged-patient process | Clinic Admin & Clinical Staff | 2027-02-12 → 2027-02-18
35 | 6.4 | Measure pilot results vs. control group | Phase 6- Pilot Campaign | 1 | 34 – 6.3 Run pilot reminder/retention campaign | Data Scientist | 2027-02-19 → 2027-02-19
36 | 7.1 | Model validation against test data & KPI targets | Phase 7- Testing, Deployment & Monitoring | 3 | 35 – 6.4 Measure pilot results vs. control group | Data Scientist | 2027-02-22 → 2027-02-24
37 | 7.2 | Assistant safety & scope testing | Phase 7- Testing, Deployment & Monitoring | 3 | 35 – 6.4 Measure pilot results vs. control group | Generative AI Developer | 2027-02-22 → 2027-02-24
38 | 7.3 | Production deployment | Phase 7- Testing, Deployment & Monitoring | 5 | 36 – 7.1 Model validation against test data & KPI targets; 37 – 7.2 Assistant safety & scope testing | IT Lead | 2027-02-25 → 2027-03-03
39 | 7.4 | Establish monitoring & retraining schedule | Phase 7- Testing, Deployment & Monitoring | 5 | 38 – 7.3 Production deployment | Data Scientist / ML Engineer | 2027-03-04 → 2027-03-10
40 | 8.1 | Train internal IT/Data team | Phase 8- Operational Handover & Closure | 3 | 39 – 7.4 Establish monitoring & retraining schedule | Project Manager / Data Scientist | 2027-03-11 → 2027-03-15
41 | 8.2 | Final presentation & documentation handover | Phase 8- Operational Handover & Closure | 1 | 40 – 8.1 Train internal IT/Data team | Project Manager | 2027-03-16 → 2027-03-16
42 | 8.3 | Project closure & lessons learned | Phase 8- Operational Handover & Closure | 1 | 41 – 8.2 Final presentation & documentation handover | Project Manager | 2027-03-17 → 2027-03-17

## Critical Path Analysis
HealthConnect Project - Critical Path Analysis (CPM)
Float = Late Start − Early Start. Float = 0 means the activity is on the critical path.
# | Code | Activity Name | Duration | Early Start | Early Finish | Late Start | Late Finish | Float (days) | Critical?
1 | 1.1 | Confirm business problem & central question | 2 | 2026-08-31 | 2026-09-01 | 2026-08-31 | 2026-09-01 | 0 | Yes
2 | 1.2 | Review data resources & confirm assumptions | 2 | 2026-08-31 | 2026-09-01 | 2026-08-31 | 2026-09-01 | 0 | Yes
3 | 1.3 | Develop Project Charter & obtain Sponsor sign-off | 7 | 2026-09-02 | 2026-09-10 | 2026-09-02 | 2026-09-10 | 0 | Yes
4 | 1.4 | Compile Stakeholder Register | 3 | 2026-09-11 | 2026-09-15 | 2026-09-11 | 2026-09-15 | 0 | Yes
5 | 1.5 | Confirm resourcing | 3 | 2026-09-11 | 2026-09-15 | 2026-09-11 | 2026-09-15 | 0 | Yes
6 | 2.1 | Develop Work Breakdown Structure | 3 | 2026-09-16 | 2026-09-18 | 2026-09-16 | 2026-09-18 | 0 | Yes
7 | 2.2 | Develop project schedule (activity durations & dependencies) | 3 | 2026-09-21 | 2026-09-23 | 2026-09-21 | 2026-09-23 | 0 | Yes
8 | 2.3 | Build network diagram & critical path analysis | 2 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | 0 | Yes
9 | 2.4 | Conduct schedule risk analysis | 2 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | 0 | Yes
10 | 2.5 | Develop Resource Management Plan | 3 | 2026-09-16 | 2026-09-18 | 2026-09-29 | 2026-10-01 | 9 | No
11 | 2.6 | Develop Communication Plan | 2 | 2026-09-16 | 2026-09-17 | 2026-09-30 | 2026-10-01 | 10 | No
12 | 2.7 | Develop Quality Management Plan | 3 | 2026-09-11 | 2026-09-15 | 2026-09-29 | 2026-10-01 | 12 | No
13 | 2.8 | Develop cost baseline / Project Budget | 3 | 2026-09-24 | 2026-09-28 | 2026-09-29 | 2026-10-01 | 3 | No
14 | 2.9 | Expand Risk Register & Dependency Register to full planning detail | 2 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | 0 | Yes
15 | 2.10 | Planning phase gate: baseline sign-off (scope, schedule, cost) | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 0 | Yes
16 | 3.1 | Data quality assessment & cleaning | 5 | 2026-10-05 | 2026-10-09 | 2026-10-05 | 2026-10-09 | 0 | Yes
17 | 3.2 | Exploratory data analysis & KPI definition | 5 | 2026-10-05 | 2026-10-09 | 2026-10-05 | 2026-10-09 | 0 | Yes
18 | 3.3 | Confirm/construct unified patient identifier | 5 | 2026-10-05 | 2026-10-09 | 2026-10-05 | 2026-10-09 | 0 | Yes
19 | 3.4 | Define no-show prediction problem | 3 | 2026-10-12 | 2026-10-14 | 2026-10-12 | 2026-10-14 | 0 | Yes
20 | 4.1 | Model design & validation approach | 4 | 2026-10-15 | 2026-10-20 | 2026-10-15 | 2026-10-20 | 0 | Yes
21 | 4.2 | Segmentation design | 4 | 2026-10-15 | 2026-10-20 | 2026-10-15 | 2026-10-20 | 0 | Yes
22 | 4.3 | ML system architecture & reproducibility design | 5 | 2026-10-21 | 2026-10-27 | 2026-10-21 | 2026-10-27 | 0 | Yes
23 | 4.4 | GenAI assistant scope & safety boundaries | 5 | 2026-10-21 | 2026-10-27 | 2026-10-21 | 2026-10-27 | 0 | Yes
24 | 4.5 | Dashboard/report design | 5 | 2026-10-21 | 2026-10-27 | 2026-10-21 | 2026-10-27 | 0 | Yes
25 | 4.6 | Phase gate: design review & Sponsor go/no-go | 1 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 0 | Yes
26 | 5.1 | Build & iteratively test no-show prediction model | 35 | 2026-10-29 | 2027-01-20 | 2026-11-12 | 2027-02-03 | 10 | No
27 | 5.2 | Build data integration / pipeline | 20 | 2026-10-29 | 2026-11-25 | 2026-11-12 | 2027-01-13 | 10 | No
28 | 5.3 | Build reproducible ML pipeline & version control | 15 | 2026-11-26 | 2027-01-20 | 2027-01-14 | 2027-02-03 | 10 | No
29 | 5.4 | Build GenAI assistant prototype | 45 | 2026-10-29 | 2027-02-03 | 2026-10-29 | 2027-02-03 | 0 | Yes
30 | 5.5 | Build dashboard/reporting | 10 | 2026-11-26 | 2027-01-13 | 2027-01-21 | 2027-02-03 | 15 | No
31 | 5.6 | Mid-development integration checkpoint | 1 | 2027-02-04 | 2027-02-04 | 2027-02-04 | 2027-02-04 | 0 | Yes
32 | 6.1 | Validate segments with clinic staff | 2 | 2027-02-05 | 2027-02-08 | 2027-02-05 | 2027-02-08 | 0 | Yes
33 | 6.2 | Train staff on dashboard & flagged-patient process | 3 | 2027-02-09 | 2027-02-11 | 2027-02-09 | 2027-02-11 | 0 | Yes
34 | 6.3 | Run pilot reminder/retention campaign | 5 | 2027-02-12 | 2027-02-18 | 2027-02-12 | 2027-02-18 | 0 | Yes
35 | 6.4 | Measure pilot results vs. control group | 1 | 2027-02-19 | 2027-02-19 | 2027-02-19 | 2027-02-19 | 0 | Yes
36 | 7.1 | Model validation against test data & KPI targets | 3 | 2027-02-22 | 2027-02-24 | 2027-02-22 | 2027-02-24 | 0 | Yes
37 | 7.2 | Assistant safety & scope testing | 3 | 2027-02-22 | 2027-02-24 | 2027-02-22 | 2027-02-24 | 0 | Yes
38 | 7.3 | Production deployment | 5 | 2027-02-25 | 2027-03-03 | 2027-02-25 | 2027-03-03 | 0 | Yes
39 | 7.4 | Establish monitoring & retraining schedule | 5 | 2027-03-04 | 2027-03-10 | 2027-03-04 | 2027-03-10 | 0 | Yes
40 | 8.1 | Train internal IT/Data team | 3 | 2027-03-11 | 2027-03-15 | 2027-03-11 | 2027-03-15 | 0 | Yes
41 | 8.2 | Final presentation & documentation handover | 1 | 2027-03-16 | 2027-03-16 | 2027-03-16 | 2027-03-16 | 0 | Yes
42 | 8.3 | Project closure & lessons learned | 1 | 2027-03-17 | 2027-03-17 | 2027-03-17 | 2027-03-17 | 0 | Yes
Critical Path (in order):
1 (1.1) → 2 (1.2) → 3 (1.3) → 4 (1.4) → 5 (1.5) → 6 (2.1) → 7 (2.2) → 8 (2.3) → 9 (2.4) → 14 (2.9) → 15 (2.10) → 16 (3.1) → 17 (3.2) → 18 (3.3) → 19 (3.4) → 20 (4.1) → 21 (4.2) → 22 (4.3) → 23 (4.4) → 24 (4.5) → 25 (4.6) → 29 (5.4) → 31 (5.6) → 32 (6.1) → 33 (6.2) → 34 (6.3) → 35 (6.4) → 36 (7.1) → 37 (7.2) → 38 (7.3) → 39 (7.4) → 40 (8.1) → 41 (8.2) → 42 (8.3)