## Budget Summary
HealthConnect Project : Budget Summary
All figures in ZAR (R). Cost baseline for the 20-week active schedule (Charter ceiling: R650,000)
Category | Budgeted Amount (R) | % of Base Budget | Notes
Labour — Data Engineer | 80000 | 13.68% | ≈50% time, Weeks 6–18
Labour — Data Scientist | 140000 | 23.93% | ≈75% time, Weeks 6–20, tapering to ≈50% Weeks 21–24
Labour — Machine Learning Engineer | 80000 | 13.68% | ≈50% time, Weeks 7–18, returning Weeks 21–23
Labour — Generative AI Developer | 80000 | 13.68% | ≈50% time, Weeks 7–18, returning Weeks 21–23
Labour — IT Lead | 65000 | 11.11% | ≈15% time Weeks 6–20, rising to ≈50% Weeks 21–23
Labour — Project Manager | 70000 | 11.97% | Full-time equivalent across all 24 weeks (PM overhead)
Compliance Officer (as-needed) | 20000 | 3.419% | Phase-gate reviews, including production readiness
Clinic Administrative & Clinical Staff (pilot) | 12000 | 2.051% | Light involvement, Weeks 18–20
Third-party LLM/API usage & tooling licences | 18000 | 3.077% | Assistant build and testing, Weeks 7–23
Cloud/hosting for production deployment | 15000 | 2.564% | Weeks 21–23
Training & handover materials | 5000 | 0.8547% | Internal IT/Data team handover, Weeks 23–24
Base Budget Subtotal | 585000
Contingency Reserve (10%) | 65000 |  | Managed per the Charter's authority matrix (draws over R10,000 require Sponsor approval)
TOTAL PROJECT BUDGET | 650000 |  | Matches the Charter's R650,000 ceiling

## Budget by Phase
HealthConnect Project - Budget by Phase (Cost Baseline)
Planned spend across all 8 phases (Initiating → Planning → Executing → Closing) plus continuous PM overhead. Base budget unchanged at R585,000.
Phase | Weeks | Planned Cost (R) | Cumulative Planned Cost (R)
Phase 1 — Project Initiation | 1–2 | 15000 | 15000
Phase 2 — Planning | 3–4 | 35000 | 50000
Phase 3 — Analysis & Data Preparation | 5–6 | 48000 | 98000
Phase 4 — Solution Design | 7–8 | 52000 | 150000
Phase 5 — Model & Assistant Development | 9–19 | 245000 | 395000
Phase 6 — Pilot Campaign | 20–21 | 45000 | 440000
Phase 7 — Testing, Deployment & Monitoring | 22–23 | 75000 | 515000
Phase 8 — Operational Handover & Closure | 24 | 25000 | 540000
Project Management overhead (continuous) | 1–24 | 45000 | 585000
TOTAL |  | 585000

## Contingency Log
HealthConnect Project - Contingency Draw Log
Contingency reserve: R65,000 (10% of base budget). Draws over R10,000 require Sponsor approval per the Charter.
Date | Description | Amount (R) | Approved By | Remaining Contingency (R) | Authority Level | Notes
— | No draws to date (Week 5 checkpoint) | 0 | — | 65000 | — | Full contingency available

## Actual vs Planned
HealthConnect Project - Actual vs Planned (Week 5 / Planning-Stage Checkpoint)
To be updated as costs are incurred; currently pre-spend beyond internal PM time
Phase | Planned Cost (R) | Actual Cost to Date (R) | Variance (R) | Variance Commentary
Phase 1 — Project Initiation | 15000 | 0 | -15000 | Complete; within budget (internal PM time only)
Phase 2 — Planning | 35000 | 0 | -35000 | Complete; within budget (internal PM time only, no external spend)
Phase 3 — Analysis & Data Preparation | 48000 | 0 | -48000 | Not yet started
Phase 4 — Solution Design | 52000 | 0 | -52000 | Not yet started
Phase 5 — Model & Assistant Development | 245000 | 0 | -245000 | Not yet started
Phase 6 — Pilot Campaign | 45000 | 0 | -45000 | Not yet started
Phase 7 — Testing, Deployment & Monitoring | 75000 | 0 | -75000 | Not yet started
Phase 8 — Operational Handover & Closure | 25000 | 0 | -25000 | Not yet started
Project Management overhead (continuous) | 45000 | 0 | -45000 | Not yet started