## Quality Mgmt Plan
HealthConnect Clinic- Quality Management Plan
Project Management Track ¦ Prepared by: Project Manager ¦ Version: 1.0 ¦ Date: 5 September 2026
1. Purpose and Quality Approach
This plan defines how quality will be planned, assured, and controlled across the HealthConnect no-show reduction project. Quality here means: the delivered model, dashboard, and assistant meet the standards set in the Project Charter, the process used to build them is auditable, and nothing is signed off without evidence. This plan does not replace the technical testing each workstream performs- it defines the project-level gates that testing must pass through.
2. Quality Objectives (from the Project Charter)
Objective | Target | Source
No-show prediction model accuracy | ≥ 75% on held-out test data | Charter, Success Criteria
At-risk patient list delivery | Monthly cadence, zero missed cycles | Charter, Success Criteria
Pilot campaign effectiveness | ≥ 10% no-show reduction in flagged segment vs. control | Charter, Success Criteria
Operational handover | Internal team runs monitoring/retraining unassisted | Charter, Success Criteria
Assistant safety | Zero out-of-scope or unsafe responses in test scenarios | Charter, Scope Statement
Regulatory compliance | Full POPIA compliance across data handling | Charter, Constraints
3. Quality Roles and Responsibilities
Role | Quality Responsibility
Project Manager | Owns this plan; runs phase-gate quality reviews; ensures no phase gate is passed without documented evidence
Data Scientist | Defines and reports model evaluation metrics (accuracy, precision, recall, F1, ROC-AUC); documents modelling limitations
Data Engineer | Defines and documents data quality checks (completeness, consistency, duplicates) before data is used downstream
Generative AI Developer | Runs assistant safety and scope test scenarios; documents escalation-handling test results
ML Engineer | Verifies pipeline reproducibility and version control before each release
Compliance Officer | Independently verifies POPIA compliance at each phase gate; sign-off is a hard gate, not advisory
Sponsor | Final go/no-go authority at each phase gate, informed by the quality evidence above

## Resource Mgmt Plan
HealthConnect Clinic- Resource Management Plan
Project Management Track ¦ Prepared by: Project Manager ¦ Version: 1.0 ¦
1. Purpose
This plan defines how human resources will be identified, acquired, organised, managed, and released across the HealthConnect no-show reduction project. It supplements the Project Charter's high-level resourcing section with the detail needed to actually run the team week to week.
2. Roles and Responsibilities
Role | Key Responsibilities | Reports To
Project Manager | Overall planning, scheduling, budget, risk/dependency management, cross-track coordination, Sponsor reporting | Sponsor
Data Engineer | Data preparation, integration/pipeline build, dashboard/reporting build, patient-identifier resolution | Project Manager
Data Scientist | EDA, KPI definition, no-show prediction model design/build/testing, pilot results measurement | Project Manager
Machine Learning Engineer | ML system architecture, reproducible pipeline, version control, model integration | Project Manager
Generative AI Developer | Assistant scope, prompt design, Knowledge Base integration, safety/scope testing | Project Manager
IT Lead | Systems access, technical review, production deployment, monitoring set-up | Project Manager
Compliance Officer | POPIA sign-off at each phase gate, including production readiness | HealthConnect Clinic (independent of PM authority)
Clinic Administrative & Clinical Staff | Segment validation, dashboard training, pilot campaign execution | Clinic Director / Practice Manager
HealthConnect Internal IT/Data Team | Receives handover training; owns monitoring/retraining after Week 24 | Clinic Director / Practice Manager
Sponsor (Clinic Director / Practice Manager) | Phase-gate approval, scope-change decisions, escalation resolution | HealthConnect Executive Committee
3. RACI Matrix- Key Deliverables
Deliverable | Project Manager | Data Eng. / Sci. / ML / GenAI | IT Lead | Compliance Officer | Sponsor
Project Charter | A/R | C | C | C | A
Data quality & identifier resolution | I | R/A | C | I | I
No-show prediction model | I | R/A | C | I | I
GenAI assistant design & build | C | R/A | C | C | I
Production deployment | A | R | R | C | I
POPIA compliance sign-off | I | C | I | R/A | I
Pilot campaign execution | A | R (Data Science) | I | I | I
Operational handover | R/A | R | R | I | A
R = Responsible, A = Accountable, C = Consulted, I = Informed.

## Resource Allocation Plan
HealthConnect Clinic- Resource Allocation Plan
Project Management Track ¦ Prepared by: Project Manager ¦ Version: 1.0 ¦ Date: 5 September 2026
1. Purpose
HealthConnect Clinic is a fictional appointment-based healthcare provider facing patient no-shows, limited visibility into why patients miss appointments, wasted appointment capacity, repetitive patient enquiries, and a need for stronger patient engagement and administrative support. This plan identifies and allocates the human, software, hardware, and other resources needed to deliver the no-show prediction model, at-risk patient dashboard, and GenAI patient assistant that address these challenges, and specifies when each resource is required across the project timeline.
2. Human Resources
Role | Addresses | Allocation (FTE) | Duration / Phase | Source | Cost Basis
Project Manager | Overall delivery, coordination, phase-gate control | 1.0 | Weeks 1–24 (full project) | Internal (AnalystLab Africa) | Day rate × duration
Data Engineer | Appointment/attendance data quality, integration, dashboard build | 1.0 | Weeks 1–16 | Internal (AnalystLab Africa) | Day rate × duration
Data Scientist | No-show driver analysis, prediction model, pilot measurement | 1.0 | Weeks 3–20 | Internal (AnalystLab Africa) | Day rate × duration
Machine Learning Engineer | Reproducible pipeline, versioning, model integration | 0.5 | Weeks 8–20 | Internal (AnalystLab Africa) | Day rate × duration
Generative AI Developer | Patient-enquiry assistant scope, prompts, safety testing | 0.75 | Weeks 6–22 | Internal (AnalystLab Africa) | Day rate × duration
IT Lead | Systems access, deployment, monitoring set-up | 0.25 | Weeks 1–24 (part-time) | HealthConnect Clinic | Existing staff time
Compliance Officer | POPIA sign-off at each phase gate | 0.1 | Weeks 1–24 (on-demand) | HealthConnect Clinic | Existing staff time
Clinic Administrative & Clinical Staff | Segment validation, dashboard use, pilot campaign execution | As needed | Weeks 14–22 (pilot window) | HealthConnect Clinic | Existing staff time
HealthConnect Internal IT/Data Team | Handover training, ongoing monitoring/retraining | 0.5 (ramping up) | Weeks 20–24 onward | HealthConnect Clinic | Existing staff time
Sponsor (Clinic Director / Practice Manager) | Phase-gate approval, escalation resolution | 0.1 | Weeks 1–24 (on-demand) | HealthConnect Clinic | Existing staff time
3. Software Resources
Resource | Purpose | Addresses | Licence / Access Type | Owner
Python (pandas, scikit-learn) / R | Data cleaning, EDA, no-show prediction model build and evaluation | Difficulty understanding no-show factors | Open source | Data Scientist / ML Engineer
Jupyter / RStudio | Modelling and analysis environment | Model development | Open source | Data Scientist
Version control (GitHub/GitLab) | Pipeline reproducibility, code review, release control | Auditability of model changes | Team licence | ML Engineer
Cloud data platform (e.g., Azure / AWS, POPIA-compliant region) | Hosting integrated appointment/attendance data, model training and scoring | Data integration for prediction | Subscription (usage-based) | Data Engineer / IT Lead
BI dashboard tool (e.g., Power BI / Tableau) | Monthly at-risk patient list and no-show driver reporting for clinic staff | Inefficient use of appointment slots; visibility into no-show factors | Subscription | Data Engineer
Clinic scheduling / practice management system (existing) | Source system for appointment, attendance, and patient contact data | Data source for the model and assistant | Existing HealthConnect licence | IT Lead
Generative AI platform + Knowledge Base (e.g., Claude API) | Patient-facing assistant for appointment and clinic-procedure enquiries | Repetitive patient enquiries; patient engagement | API subscription (usage-based) | GenAI Developer
Messaging/notification channel (SMS or WhatsApp Business API) | Delivering reminders and pilot campaign messages to at-risk patients | Pilot campaign to reduce no-shows | Subscription (usage-based) | Data Engineer / Clinic Admin
Project management tool (e.g., Asana) | Task tracking, phase-gate evidence, risk/comms tracking | Project governance | Team licence | Project Manager
Document/collaboration suite (e.g., Microsoft 365 / Google Workspace) | Plans, registers, reporting, phase-gate documentation | Project governance | Existing HealthConnect / AnalystLab licence | Project Manager
4. Hardware Resources
Resource | Purpose | Quantity | Provided By
Project team laptops/workstations | Development, analysis, and administrative work for the project team | 1 per project team member (≈ 5) | AnalystLab Africa
Cloud compute (model training/scoring instances) | Training and running the no-show prediction model at scale | Provisioned on demand (cloud) | Cloud provider (Azure/AWS)
Cloud/application hosting (dashboard and GenAI assistant) | Hosting the dashboard and patient assistant for clinic use | Provisioned on demand (cloud) | Cloud provider (Azure/AWS)
Clinic workstations / tablets (existing) | Clinic staff access to the at-risk patient dashboard | Existing clinic devices, reused | HealthConnect Clinic
Network and security infrastructure (existing) | Secure, POPIA-compliant connectivity between clinic systems and the project environment | Existing HealthConnect infrastructure | HealthConnect Clinic IT
5. Other Resources (Facilities, Data, Governance)
Resource | Purpose | Addresses
Historical appointment and attendance data (12+ months, de-identified) | Training and validating the no-show prediction model | Difficulty understanding factors associated with no-shows
POPIA compliance framework / data processing agreement | Lawful handling of patient data across the project | Regulatory compliance
Meeting space / virtual meeting rooms | Phase-gate reviews, stakeholder workshops, pilot planning sessions | Project governance and stakeholder engagement
Control group segment (patients not receiving the intervention) | Measuring pilot campaign effectiveness against a baseline | Pilot campaign effectiveness measurement
FTE = Full-Time Equivalent. Allocation figures are indicative planning estimates and should be refined once the detailed schedule is confirmed.