## Task Tracker
HealthConnect Project - Task Tracker (Week 5 Checkpoint)
Reflects the corrected WBS: Initiating → Planning → Executing → Closing. Week 5 = Planning stage delivered.
Code | Task Name | Phase | Owner | Priority | Status | % Complete | Start Date | End Date | Notes
1.1 | Confirm business problem & central question | Phase 1 - Project Initiation | Project Manager | High | Complete | 100 | 2026-08-31 | 2026-09-01
1.2 | Review data resources & confirm assumptions | Phase 1 - Project Initiation | Project Manager | High | Complete | 100 | 2026-08-31 | 2026-09-01
1.3 | Develop Project Charter & obtain Sponsor sign-off | Phase 1 - Project Initiation | Project Manager | High | Complete | 100 | 2026-09-02 | 2026-09-10 | Charter drafted; Sponsor sign-off carried as an open item into Planning
1.4 | Compile Stakeholder Register | Phase 1 - Project Initiation | Project Manager | High | Complete | 100 | 2026-09-11 | 2026-09-15
1.5 | Confirm resourcing | Phase 1 - Project Initiation | Project Manager | High | Complete | 100 | 2026-09-11 | 2026-09-15
2.1 | Develop Work Breakdown Structure | Phase 2 - Planning | Project Manager | High | Complete | 100 | 2026-09-16 | 2026-09-18
2.2 | Develop project schedule (activity durations & dependencies) | Phase 2 - Planning | Project Manager | High | Complete | 100 | 2026-09-21 | 2026-09-23
2.3 | Build network diagram & critical path analysis | Phase 2 - Planning | Project Manager | High | Complete | 100 | 2026-09-24 | 2026-09-25
2.4 | Conduct schedule risk analysis | Phase 2 - Planning | Project Manager | High | Complete | 100 | 2026-09-28 | 2026-09-29
2.5 | Develop Resource Management Plan | Phase 2 - Planning | Project Manager | Medium | Complete | 100 | 2026-09-16 | 2026-09-18
2.6 | Develop Communication Plan | Phase 2 - Planning | Project Manager | Low | Complete | 100 | 2026-09-16 | 2026-09-17
2.7 | Develop Quality Management Plan | Phase 2 - Planning | Project Manager | Medium | Complete | 100 | 2026-09-11 | 2026-09-15
2.8 | Develop cost baseline / Project Budget | Phase 2 - Planning | Project Manager | Medium | Complete | 100 | 2026-09-24 | 2026-09-28
2.9 | Expand Risk Register & Dependency Register to full planning detail | Phase 2 - Planning | Project Manager | High | Complete | 100 | 2026-09-30 | 2026-10-01
2.10 | Planning phase gate: baseline sign-off (scope, schedule, cost) | Phase 2 - Planning | Project Manager / Sponsor | High | In Progress | 80 | 2026-10-02 | 2026-10-02 | Awaiting Sponsor sign-off on the scope/schedule/cost baseline
3.1 | Data quality assessment & cleaning | Phase 3 - Analysis & Data Preparation | Data Engineer | High | Not Started | 0 | 2026-10-05 | 2026-10-09
3.2 | Exploratory data analysis & KPI definition | Phase 3 - Analysis & Data Preparation | Data Scientist | High | Not Started | 0 | 2026-10-05 | 2026-10-09
3.3 | Confirm/construct unified patient identifier | Phase 3 - Analysis & Data Preparation | Data Engineer | High | Not Started | 0 | 2026-10-05 | 2026-10-09 | Flagged at risk pending confirmed patient identifier - see risk register
3.4 | Define no-show prediction problem | Phase 3 - Analysis & Data Preparation | Data Scientist | High | Not Started | 0 | 2026-10-12 | 2026-10-14
4.1 | Model design & validation approach | Phase 4 - Solution Design | Data Scientist | High | Not Started | 0 | 2026-10-15 | 2026-10-20
4.2 | Segmentation design | Phase 4 - Solution Design | Data Scientist | High | Not Started | 0 | 2026-10-15 | 2026-10-20
4.3 | ML system architecture & reproducibility design | Phase 4 - Solution Design | ML Engineer | High | Not Started | 0 | 2026-10-21 | 2026-10-27
4.4 | GenAI assistant scope & safety boundaries | Phase 4 - Solution Design | Generative AI Developer | High | Not Started | 0 | 2026-10-21 | 2026-10-27
4.5 | Dashboard/report design | Phase 4 - Solution Design | Data Engineer | High | Not Started | 0 | 2026-10-21 | 2026-10-27
4.6 | Phase gate: design review & Sponsor go/no-go | Phase 4 - Solution Design | Project Manager / Sponsor | High | Not Started | 0 | 2026-10-28 | 2026-10-28
5.1 | Build & iteratively test no-show prediction model | Phase 5 - Model & Assistant Development | Data Scientist | Medium | Not Started | 0 | 2026-10-29 | 2027-01-20
5.2 | Build data integration / pipeline | Phase 5 - Model & Assistant Development | Data Engineer | Medium | Not Started | 0 | 2026-10-29 | 2026-11-25
5.3 | Build reproducible ML pipeline & version control | Phase 5 - Model & Assistant Development | ML Engineer | Medium | Not Started | 0 | 2026-11-26 | 2027-01-20
5.4 | Build GenAI assistant prototype | Phase 5 - Model & Assistant Development | Generative AI Developer | High | Not Started | 0 | 2026-10-29 | 2027-02-03
5.5 | Build dashboard/reporting | Phase 5 - Model & Assistant Development | Data Engineer | Medium | Not Started | 0 | 2026-11-26 | 2027-01-13
5.6 | Mid-development integration checkpoint | Phase 5 - Model & Assistant Development | Project Manager | High | Not Started | 0 | 2027-02-04 | 2027-02-04
6.1 | Validate segments with clinic staff | Phase 6 - Pilot Campaign | Clinic Admin & Clinical Staff | High | Not Started | 0 | 2027-02-05 | 2027-02-08
6.2 | Train staff on dashboard & flagged-patient process | Phase 6 - Pilot Campaign | Project Manager | High | Not Started | 0 | 2027-02-09 | 2027-02-11
6.3 | Run pilot reminder/retention campaign | Phase 6 - Pilot Campaign | Clinic Admin & Clinical Staff | High | Not Started | 0 | 2027-02-12 | 2027-02-18
6.4 | Measure pilot results vs. control group | Phase 6 - Pilot Campaign | Data Scientist | High | Not Started | 0 | 2027-02-19 | 2027-02-19
7.1 | Model validation against test data & KPI targets | Phase 7 - Testing, Deployment & Monitoring | Data Scientist | High | Not Started | 0 | 2027-02-22 | 2027-02-24
7.2 | Assistant safety & scope testing | Phase 7 - Testing, Deployment & Monitoring | Generative AI Developer | High | Not Started | 0 | 2027-02-22 | 2027-02-24
7.3 | Production deployment | Phase 7 - Testing, Deployment & Monitoring | IT Lead | High | Not Started | 0 | 2027-02-25 | 2027-03-03
7.4 | Establish monitoring & retraining schedule | Phase 7 - Testing, Deployment & Monitoring | Data Scientist / ML Engineer | High | Not Started | 0 | 2027-03-04 | 2027-03-10
8.1 | Train internal IT/Data team | Phase 8 - Operational Handover & Closure | Project Manager / Data Scientist | High | Not Started | 0 | 2027-03-11 | 2027-03-15
8.2 | Final presentation & documentation handover | Phase 8 - Operational Handover & Closure | Project Manager | High | Not Started | 0 | 2027-03-16 | 2027-03-16
8.3 | Project closure & lessons learned | Phase 8 - Operational Handover & Closure | Project Manager | High | Not Started | 0 | 2027-03-17 | 2027-03-17

## Updated Timeline
HealthConnect Project - Updated Detailed Timeline (Week 5 Checkpoint)
31 Aug 2026 – 2027-03-17 (24 working weeks; December fully excluded)
Major Phase | Key Activity | Milestone | Start Date | End Date | Status | Depends On
Phase 1 - Project Initiation (2026-08-31 to 2026-09-15) | • 1.1 Confirm business problem & central question |  | 2026-08-31 | 2026-09-01 | Complete | -
| • 1.2 Review data resources & confirm assumptions |  | 2026-08-31 | 2026-09-01 | Complete | -
| • 1.3 Develop Project Charter & obtain Sponsor sign-off |  | 2026-09-02 | 2026-09-10 | Complete | 1.1; 1.2
| • 1.4 Compile Stakeholder Register |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| • 1.5 Confirm resourcing |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| Milestone | Project Charter approved by Sponsor | 2026-09-15 | 2026-09-15 | Pending sign-off
Phase 2 - Planning (2026-09-16 to 2026-10-02) | • 2.1 Develop Work Breakdown Structure |  | 2026-09-16 | 2026-09-18 | Complete | 1.4; 1.5
| • 2.2 Develop project schedule (activity durations & dependencies) |  | 2026-09-21 | 2026-09-23 | Complete | 2.1
| • 2.3 Build network diagram & critical path analysis |  | 2026-09-24 | 2026-09-25 | Complete | 2.2
| • 2.4 Conduct schedule risk analysis |  | 2026-09-28 | 2026-09-29 | Complete | 2.3
| • 2.5 Develop Resource Management Plan |  | 2026-09-16 | 2026-09-18 | Complete | 1.4; 1.5
| • 2.6 Develop Communication Plan |  | 2026-09-16 | 2026-09-17 | Complete | 1.4
| • 2.7 Develop Quality Management Plan |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| • 2.8 Develop cost baseline / Project Budget |  | 2026-09-24 | 2026-09-28 | Complete | 2.2
| • 2.9 Expand Risk Register & Dependency Register to full planning detail |  | 2026-09-30 | 2026-10-01 | Complete | 2.4
| • 2.10 Planning phase gate: baseline sign-off (scope, schedule, cost) |  | 2026-10-02 | 2026-10-02 | In Progress | 2.4; 2.5; 2.6; 2.7; 2.8; 2.9
| Milestone | Planning phase gate: baseline sign-off (scope, schedule, cost) | 2026-10-02 | 2026-10-02 | Pending sign-off
Phase 3 - Analysis & Data Preparation (2026-10-05 to 2026-10-14) | • 3.1 Data quality assessment & cleaning |  | 2026-10-05 | 2026-10-09 | Not Started | 2.10
| • 3.2 Exploratory data analysis & KPI definition |  | 2026-10-05 | 2026-10-09 | Not Started | 2.10
| • 3.3 Confirm/construct unified patient identifier |  | 2026-10-05 | 2026-10-09 | Not Started | 2.10
| • 3.4 Define no-show prediction problem |  | 2026-10-12 | 2026-10-14 | Not Started | 3.1; 3.2; 3.3
| Milestone | No-show prediction problem formally defined | 2026-10-14 | 2026-10-14 | Not due
Phase 4 - Solution Design (2026-10-15 to 2026-10-28) | • 4.1 Model design & validation approach |  | 2026-10-15 | 2026-10-20 | Not Started | 3.4
| • 4.2 Segmentation design |  | 2026-10-15 | 2026-10-20 | Not Started | 3.4
| • 4.3 ML system architecture & reproducibility design |  | 2026-10-21 | 2026-10-27 | Not Started | 4.1; 4.2
| • 4.4 GenAI assistant scope & safety boundaries |  | 2026-10-21 | 2026-10-27 | Not Started | 4.1; 4.2
| • 4.5 Dashboard/report design |  | 2026-10-21 | 2026-10-27 | Not Started | 4.1; 4.2
| • 4.6 Phase gate: design review & Sponsor go/no-go |  | 2026-10-28 | 2026-10-28 | Not Started | 4.3; 4.4; 4.5
| Milestone | Design approved at Phase Gate (Sponsor go/no-go) | 2026-10-28 | 2026-10-28 | Not due
Phase 5 - Model & Assistant Development (2026-10-29 to 2027-02-04) | • 5.1 Build & iteratively test no-show prediction model |  | 2026-10-29 | 2027-01-20 | Not Started | 4.6
| • 5.2 Build data integration / pipeline |  | 2026-10-29 | 2026-11-25 | Not Started | 4.6
| • 5.3 Build reproducible ML pipeline & version control |  | 2026-11-26 | 2027-01-20 | Not Started | 5.2
| • 5.4 Build GenAI assistant prototype |  | 2026-10-29 | 2027-02-03 | Not Started | 4.6
| • 5.5 Build dashboard/reporting |  | 2026-11-26 | 2027-01-13 | Not Started | 5.2
| • 5.6 Mid-development integration checkpoint |  | 2027-02-04 | 2027-02-04 | Not Started | 5.1; 5.3; 5.4; 5.5
| Milestone | Mid-development integration checkpoint | 2027-02-04 | 2027-02-04 | Not due
Phase 6 - Pilot Campaign (2027-02-05 to 2027-02-19) | • 6.1 Validate segments with clinic staff |  | 2027-02-05 | 2027-02-08 | Not Started | 5.6
| • 6.2 Train staff on dashboard & flagged-patient process |  | 2027-02-09 | 2027-02-11 | Not Started | 6.1
| • 6.3 Run pilot reminder/retention campaign |  | 2027-02-12 | 2027-02-18 | Not Started | 6.2
| • 6.4 Measure pilot results vs. control group |  | 2027-02-19 | 2027-02-19 | Not Started | 6.3
| Milestone | Pilot results measured against control group | 2027-02-19 | 2027-02-19 | Not due
Phase 7 - Testing, Deployment & Monitoring (2027-02-22 to 2027-03-10) | • 7.1 Model validation against test data & KPI targets |  | 2027-02-22 | 2027-02-24 | Not Started | 6.4
| • 7.2 Assistant safety & scope testing |  | 2027-02-22 | 2027-02-24 | Not Started | 6.4
| • 7.3 Production deployment |  | 2027-02-25 | 2027-03-03 | Not Started | 7.1; 7.2
| • 7.4 Establish monitoring & retraining schedule |  | 2027-03-04 | 2027-03-10 | Not Started | 7.3
| Milestone | Model and assistant live in production | 2027-03-10 | 2027-03-10 | Not due
Phase 8 - Operational Handover & Closure (2027-03-11 to 2027-03-17) | • 8.1 Train internal IT/Data team |  | 2027-03-11 | 2027-03-15 | Not Started | 7.4
| • 8.2 Final presentation & documentation handover |  | 2027-03-16 | 2027-03-16 | Not Started | 8.1
| • 8.3 Project closure & lessons learned |  | 2027-03-17 | 2027-03-17 | Not Started | 8.2
| Milestone | Operational handover complete; project closed | 2027-03-17 | 2027-03-17 | Not due

## Updated Risk Register
HealthConnect Project — Updated Risk Register (Week 5 Checkpoint)
Risk Score = Likelihood value × Impact value (see scale, cols K:L). New: R13 (schedule extension)
ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner | Status | Scale
R1 | Data quality issues in the appointment dataset (missing, inconsistent, or unclear fields) | Data | High | High | 9 | Early data quality assessment planned for Phase 3 (3.1); document assumptions and cleaning steps before modelling | Data Engineer | Monitoring | Level | Value
R2 | No-show prediction model accuracy falls below the 75% target | Model | Medium | High | 6 | Iterative build-test cycles (5.1); feature engineering review if early accuracy lags | Data Scientist | Open | Low | 1
R3 | Low staff adoption of at-risk patient flags and reminder recommendations | Adoption | Medium | Medium | 4 | Early staff involvement in segment validation (6.1) and structured training (6.2) | Project Manager | Open | Medium | 2
R4 | Generative AI assistant produces out-of-scope or unsafe responses (e.g., clinical advice) | Safety / Compliance | Medium | High | 6 | Strict Knowledge-Base-only design (4.4); dedicated safety and scope testing (7.2) | Generative AI Developer | Open | High | 3
R5 | Insufficient internal capacity at HealthConnect to sustain monitoring and retraining after handover | Operational | Medium | High | 6 | Confirm internal team availability early (DEP-008); structured handover training (8.1) | Project Manager | Open
R6 | Data privacy / POPIA compliance exposure given health-related patient data | Compliance | Medium | High | 6 | Compliance Officer sign-off at each phase gate; consent status confirmed early (DEP-003) | Compliance Officer | Monitoring
R7 | Schedule pressure from the December office closure falling within the project timeline | Schedule | High | Medium | 6 | December fully excluded from the active schedule; work resumes after the recess with buffer | Project Manager | Open
R8 | Dependency on third-party LLM/API availability, rate limits, or cost for the assistant | Technical / Vendor | Low | Medium | 2 | Early API access testing (5.4); fallback/offline model option identified | IT Lead | Open
R9 | Scope creep beyond the agreed prototype/pilot boundary into full production rollout without sign-off | Scope | Low | High | 3 | Reinforce Scope Statement; Sponsor sign-off required through change control for any scope change | Project Manager | Open
R10 | Budget overrun beyond the approved contingency due to unforeseen integration complexity | Financial | Low | Medium | 2 | Weekly budget tracking (9.2); contingency draws logged and approved per the authority matrix | Project Manager | Open
R11 | Initial data quality findings indicate more missing/inconsistent values than assumed at Charter stage | Data | High | Medium | 6 | Extend Phase 3 buffer if needed; escalate scale of the issue for a revised effort estimate | Project Manager | Monitoring
R12 | IT Lead has a capacity conflict with commitments outside the project, risking delays to identifier resolution and deployment support | Resource | Medium | Medium | 4 | Confirm dedicated hours with the IT Lead's line manager; escalate to Sponsor if unresolved | Project Manager | Monitoring
R13 | Formal Planning-stage CPM analysis shows the realistic project duration is ~24 weeks, not the originally assumed 20 | Schedule | High | Medium | 6 | Baseline the 24-week schedule at the Planning phase gate (2.10) rather than silently compressing it; flag to Sponsor for awareness | Project Manager | New — identified in Planning

## Updated Dependency Register
HealthConnect Project — Updated Dependency Register (Week 5 Checkpoint)
Tracked separately from the Risk Register
Dependency ID | Dependency / Description | Dependent Activity/Task | Dependency Type | Source / Owner | Required By | Status | Impact if Delayed | Criticality | Mitigation / Action | Responsible Person | Notes
DEP-001 | Confirmed access to the HealthConnect Appointment Dataset, usable for analysis and modelling | 3.1 Data quality assessment & cleaning | Internal / Data | IT Lead | 2026-10-05 | Complete | Data preparation and modelling timeline slips | High | N/A — resolved | Data Engineer | Access confirmed during Initiating
DEP-002 | A common (or derivable) patient identifier confirmed across scheduling and reminder records | 3.3 Confirm/construct unified patient identifier | Technical | IT Lead | 2026-10-09 | At Risk | Data integration requires rework | Critical | Build a matching/linking key as a fallback; escalated via DEP-009 | Data Engineer | Early review suggests no clean shared identifier exists
DEP-003 | POPIA consent status confirmed for the appointment data used in the project | 1.2 Review data resources & confirm assumptions | Regulatory / Compliance | Compliance Officer | 2026-09-01 | Complete | Project pauses pending compliance clearance | Critical | N/A — resolved | Project Manager | Confirmed by Compliance Officer during Initiating
DEP-004 | Finalised, Sponsor-approved Clinic Knowledge Base scope for the patient information assistant | 4.4 GenAI assistant scope & safety boundaries | Internal / Content | Clinic Administration | 2026-10-27 | In Progress | Assistant scope and safety boundaries remain undefined | High | Draft an interim scope for Sponsor approval if the final Knowledge Base is delayed | Project Manager
DEP-005 | Administrative and clinical staff availability for segment validation and pilot execution | 6.1 Validate segments with clinic staff | Resource | Clinic Administrative & Clinical Staff | 2027-02-05 | Not Started | Pilot campaign delayed or under-resourced | Medium | Confirm staff resourcing at the Phase 4 gate | Project Manager
DEP-006 | Third-party LLM/API access, licensing terms, and usage limits confirmed | 5.4 Build GenAI assistant prototype | External / Vendor | IT Lead / LLM Provider | 2026-10-29 | Not Started | Assistant build blocked or delayed | Medium | Identify a fallback or offline model option | IT Lead
DEP-007 | Production environment / hosting readiness for the model, dashboard, and assistant | 7.3 Production deployment | Technical | IT Lead | 2027-02-25 | Not Started | Deployment slips past the planned date | High | Confirm environment readiness early in Phase 5 | IT Lead
DEP-008 | HealthConnect internal IT/Data team nominated and available for handover training | 8.1 Train internal IT/Data team | Resource / Internal | Clinic Management | 2027-03-11 | Not Started | Handover delayed; consultant support required beyond project close | High | Confirm nominated staff at the Phase 7 gate | Project Manager
DEP-009 | Confirmed dedicated IT Lead capacity, prioritised against the IT Lead's other commitments | 3.3 Confirm/construct unified patient identifier; ongoing IT support | Resource | IT Lead's Line Manager | 2026-10-09 | At Risk | Identifier resolution and later deployment support both delayed | Medium | Escalate to Sponsor if unresolved by the next cross-track check-in | Project Manager | Raised via Week 5 coordination
DEP-010 | Sponsor sign-off on the Planning-stage baseline (scope, schedule, cost) confirming the ~24-week duration | 3.1 Data quality assessment & cleaning (Phase 3 start) | Internal / Governance | Sponsor | 2026-10-02 | In Progress | Phase 3 cannot formally start without an approved baseline | Critical | Present the Read Me findings (Timeline vs Schedule) at the next steering review | Project Manager | New — identified at the Planning phase gate