## Final Workstream Status
HealthConnect Project — Final Workstream Status
Honest status as of Week 8. This is a foundational-stage proof of concept, not a completed production system.
Workstream | Final Deliverable This Stage | Status | Evidence | What Remains
Project Management | Full Initiating/Planning documentation set; integration and testing coordination through Week 7 | Complete for this stage | Charter, Schedule, Risk/Dependency Registers, Testing Records (Weeks 4–7) | Coordinate Phases 5–8 (build, pilot, deployment, handover) as the project continues
Data Analytics | Validated KPIs and no-show findings, refined dashboard | Complete for this stage | Week 6–7 validated findings, retested at full Phase 3 scale | Ongoing monitoring once the model and dashboard are in active use
Data Science | Candidate no-show prediction model, tested and compared to baseline | In progress | Week 6 model comparison; Week 7 testing under way at Week 7 checkpoint | Finalise model selection and complete Phase 5 build
ML Engineering | Initial pipeline integration and validation | In progress | Week 6 integration; Week 7 component testing | Full pipeline build and reliability hardening in Phase 5
Generative AI | Refined, safety-tested patient information assistant prototype | Complete for this stage | Week 6–7 refinement and retesting against an expanded scenario set | Full assistant build within Phase 5; production integration in Phase 7

## Updated Timeline
HealthConnect Project — Updated Timeline (Final Checkpoint, Week 8)
Phase 4 gate passed; Phase 5 (Model & Assistant Development) now under way. Phases 6–8 remain ahead.
Major Phase | Key Activity | Milestone | Start Date | End Date | Status | Depends On
Phase 1 — Project Initiation (2026-08-31 to 2026-09-15) | • 1.1 Confirm business problem & central question |  | 2026-08-31 | 2026-09-01 | Complete | —
| • 1.2 Review data resources & confirm assumptions |  | 2026-08-31 | 2026-09-01 | Complete | —
| • 1.3 Develop Project Charter & obtain Sponsor sign-off |  | 2026-09-02 | 2026-09-10 | Complete | 1.1; 1.2
| • 1.4 Compile Stakeholder Register |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| • 1.5 Confirm resourcing |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| Milestone | Project Charter approved by Sponsor | 2026-09-15 | 2026-09-15 | Achieved
Phase 2 — Planning (2026-09-16 to 2026-10-02) | • 2.1 Develop Work Breakdown Structure |  | 2026-09-16 | 2026-09-18 | Complete | 1.4; 1.5
| • 2.2 Develop project schedule (activity durations & dependencies) |  | 2026-09-21 | 2026-09-23 | Complete | 2.1
| • 2.3 Build network diagram & critical path analysis |  | 2026-09-24 | 2026-09-25 | Complete | 2.2
| • 2.4 Conduct schedule risk analysis |  | 2026-09-28 | 2026-09-29 | Complete | 2.3
| • 2.5 Develop Resource Management Plan |  | 2026-09-16 | 2026-09-18 | Complete | 1.4; 1.5
| • 2.6 Develop Communication Plan |  | 2026-09-16 | 2026-09-17 | Complete | 1.4
| • 2.7 Develop Quality Management Plan |  | 2026-09-11 | 2026-09-15 | Complete | 1.3
| • 2.8 Develop cost baseline / Project Budget |  | 2026-09-24 | 2026-09-28 | Complete | 2.2
| • 2.9 Expand Risk Register & Dependency Register to full planning detail |  | 2026-09-30 | 2026-10-01 | Complete | 2.4
| • 2.10 Planning phase gate: baseline sign-off (scope, schedule, cost) |  | 2026-10-02 | 2026-10-02 | Complete | 2.4; 2.5; 2.6; 2.7; 2.8; 2.9
| Milestone | Planning phase gate: baseline sign-off (scope, schedule, cost) | 2026-10-02 | 2026-10-02 | Achieved
Phase 3 — Analysis & Data Preparation (2026-10-05 to 2026-10-14) | • 3.1 Data quality assessment & cleaning |  | 2026-10-05 | 2026-10-09 | Complete | 2.10
| • 3.2 Exploratory data analysis & KPI definition |  | 2026-10-05 | 2026-10-09 | Complete | 2.10
| • 3.3 Confirm/construct unified patient identifier |  | 2026-10-05 | 2026-10-09 | Complete | 2.10
| • 3.4 Define no-show prediction problem |  | 2026-10-12 | 2026-10-14 | Complete | 3.1; 3.2; 3.3
| Milestone | No-show prediction problem formally defined | 2026-10-14 | 2026-10-14 | Achieved — validated
Phase 4 — Solution Design (2026-10-15 to 2026-10-28) | • 4.1 Model design & validation approach |  | 2026-10-15 | 2026-10-20 | Complete | 3.4
| • 4.2 Segmentation design |  | 2026-10-15 | 2026-10-20 | Complete | 3.4
| • 4.3 ML system architecture & reproducibility design |  | 2026-10-21 | 2026-10-27 | Complete | 4.1; 4.2
| • 4.4 GenAI assistant scope & safety boundaries |  | 2026-10-21 | 2026-10-27 | Complete | 4.1; 4.2
| • 4.5 Dashboard/report design |  | 2026-10-21 | 2026-10-27 | Complete | 4.1; 4.2
| • 4.6 Phase gate: design review & Sponsor go/no-go |  | 2026-10-28 | 2026-10-28 | Complete | 4.3; 4.4; 4.5
| Milestone | Design approved at Phase Gate (Sponsor go/no-go) | 2026-10-28 | 2026-10-28 | Achieved this week
Phase 5 — Model & Assistant Development (2026-10-29 to 2027-02-04) | • 5.1 Build & iteratively test no-show prediction model |  | 2026-10-29 | 2027-01-20 | In Progress | 4.6
| • 5.2 Build data integration / pipeline |  | 2026-10-29 | 2026-11-25 | In Progress | 4.6
| • 5.3 Build reproducible ML pipeline & version control |  | 2026-11-26 | 2027-01-20 | Not Started | 5.2
| • 5.4 Build GenAI assistant prototype |  | 2026-10-29 | 2027-02-03 | Not Started | 4.6
| • 5.5 Build dashboard/reporting |  | 2026-11-26 | 2027-01-13 | Not Started | 5.2
| • 5.6 Mid-development integration checkpoint |  | 2027-02-04 | 2027-02-04 | Not Started | 5.1; 5.3; 5.4; 5.5
| Milestone | Mid-development integration checkpoint | 2027-02-04 | 2027-02-04 | Not due
Phase 6 — Pilot Campaign (2027-02-05 to 2027-02-19) | • 6.1 Validate segments with clinic staff |  | 2027-02-05 | 2027-02-08 | Not Started | 5.6
| • 6.2 Train staff on dashboard & flagged-patient process |  | 2027-02-09 | 2027-02-11 | Not Started | 6.1
| • 6.3 Run pilot reminder/retention campaign |  | 2027-02-12 | 2027-02-18 | Not Started | 6.2
| • 6.4 Measure pilot results vs. control group |  | 2027-02-19 | 2027-02-19 | Not Started | 6.3
| Milestone | Pilot results measured against control group | 2027-02-19 | 2027-02-19 | Not due
Phase 7 — Testing, Deployment & Monitoring (2027-02-22 to 2027-03-10) | • 7.1 Model validation against test data & KPI targets |  | 2027-02-22 | 2027-02-24 | Not Started | 6.4
| • 7.2 Assistant safety & scope testing |  | 2027-02-22 | 2027-02-24 | Not Started | 6.4
| • 7.3 Production deployment |  | 2027-02-25 | 2027-03-03 | Not Started | 7.1; 7.2
| • 7.4 Establish monitoring & retraining schedule |  | 2027-03-04 | 2027-03-10 | Not Started | 7.3
| Milestone | Model and assistant live in production | 2027-03-10 | 2027-03-10 | Not due
Phase 8 — Operational Handover & Closure (2027-03-11 to 2027-03-17) | • 8.1 Train internal IT/Data team |  | 2027-03-11 | 2027-03-15 | Not Started | 7.4
| • 8.2 Final presentation & documentation handover |  | 2027-03-16 | 2027-03-16 | Not Started | 8.1
| • 8.3 Project closure & lessons learned |  | 2027-03-17 | 2027-03-17 | Not Started | 8.2
| Milestone | Operational handover complete; project closed | 2027-03-17 | 2027-03-17 | Not due

## Final Dependency Register
HealthConnect Project — Final Dependency Register
Full history preserved; only unresolved items require action going forward
Dependency ID | Dependency / Description | Dependent Activity/Task | Dependency Type | Source / Owner | Required By | Status | Impact if Delayed | Criticality | Mitigation / Action | Responsible Person | Notes
DEP-002 | A common (or derivable) patient identifier confirmed across scheduling and reminder records | 3.3 Confirm/construct unified patient identifier | Technical | Data Engineer | 2026-10-09 | Validated | Data integration would require rework | Critical | Fallback linking key tested at full Phase 3 scale (Week 7) | Data Engineer | Closed — no further action
DEP-004 | Finalised, Sponsor-approved Clinic Knowledge Base scope for the patient information assistant | 4.4 GenAI assistant scope & safety boundaries | Content / Governance | Generative AI Developer | 2026-10-27 | Validated | Assistant scope could remain unreliable under real use | High | Retested against an expanded scenario set (Week 7) | Generative AI Developer | Closed — no further action
DEP-009 | Confirmed dedicated IT Lead capacity, prioritised against the IT Lead's other commitments | 3.3 Confirm/construct unified patient identifier; ongoing IT support | Resource | IT Lead's Line Manager | 2026-10-09 | Open — unresolved | Identifier resolution and later deployment support both delayed | Medium | Escalated twice (Weeks 6–7); still awaiting a Sponsor resourcing decision | Project Manager | Carried into Phase 5 as a live risk — not resolved by testing alone
DEP-011 | Data Science candidate model interface (input/output format) needed before pipeline integration work can begin | 5.3 Build reproducible ML pipeline & version control | Technical | Data Scientist | Phase 5 | Open — in progress | ML Engineering integration work blocked at the start of full Phase 5 build | Medium | Being defined as Data Science finalises model selection in Phase 5 | Data Scientist / ML Engineer | On track; not yet a blocker
DEP-013 | Sponsor decision on IT Lead resourcing conflict, required before Phase 7 deployment planning | 7.3 Production deployment | Governance | Sponsor | Before Phase 7 | Deployment support unavailable if unresolved | High | Raised as an explicit item for the final presentation and Sponsor review | Project Manager | New — formalises DEP-009 as a named decision the Sponsor must make

## Final Risk Register
HealthConnect Project — Final Risk Register
Risk Score = Likelihood value × Impact value (see scale, cols K:L). Reflects status at the end of Week 8.
ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner | Status | Scale
R1 | Data quality issues in the appointment dataset | Data | Low | Medium | 2 | Validated at full Phase 3 scale; exclusion rule applied | Data Engineer | Closed — validated | Level | Value
R2 | No-show prediction model accuracy falls below the 75% target | Model | Medium | High | 6 | Testing in progress at Week 7 checkpoint; final result due in Phase 5 | Data Scientist | Open — in progress | Low | 1
R3 | Low staff adoption of at-risk patient flags and reminder recommendations | Adoption | Medium | Medium | 4 | Staff involvement planned ahead of the Phase 6 pilot | Project Manager | Open — not yet due | Medium | 2
R4 | Generative AI assistant produces out-of-scope or unsafe responses | Safety / Compliance | Low | High | 3 | Retested under an expanded scenario set; confirmed stable | Generative AI Developer | Closed — validated | High | 3
R5 | Insufficient internal capacity at HealthConnect to sustain monitoring and retraining after handover | Operational | Medium | High | 6 | To be confirmed ahead of Phase 8 | Project Manager | Open — not yet due
R6 | Data privacy / POPIA compliance exposure given health-related patient data | Compliance | Medium | High | 6 | Compliance Officer sign-off required at each remaining phase gate | Compliance Officer | Monitoring
R7 | Schedule pressure from the December office closure falling within the project timeline | Schedule | High | Medium | 6 | December fully excluded from the active schedule; still ahead in Phase 5 | Project Manager | Open — not yet due
R8 | Dependency on third-party LLM/API availability, rate limits, or cost for the assistant | Technical / Vendor | Low | Medium | 2 | Fallback/offline model option identified | IT Lead | Open — not yet due
R9 | Scope creep beyond the agreed prototype/pilot boundary into full production rollout without sign-off | Scope | Low | High | 3 | Scope Statement holding; no changes requested to date | Project Manager | Open — monitoring
R10 | Budget overrun beyond the approved contingency | Financial | Low | Medium | 2 | No contingency draws to date | Project Manager | Open — monitoring
R12 | IT Lead has a capacity conflict with commitments outside the project | Resource | Medium | Medium | 4 | Escalated twice; formalised as DEP-013 for Sponsor decision | Project Manager | Escalated — unresolved
R14 | Data Science model interface not yet finalised | Technical / Integration | Low | Low | 1 | Being defined in Phase 5; not yet a blocker | Data Scientist / ML Engineer | Open — monitoring
R17 | Foundational-stage work (this Experience Lab) could be mistaken for a completed, production-ready system | Communication | Medium | Medium | 4 | Final presentation explicitly states current phase, evidence, and remaining work — no overclaiming | Project Manager | New — managed via presentation framing

## Final Decision Log
HealthConnect Project — Final Decision Log
All major decisions across the Experience Lab, consolidated
ID | Decision | Rationale | Made By | Date | Impact
DEC-01 | Adopt the ~24-week CPM-derived schedule as the formal project baseline | Compression to 20 weeks would consume float from the least-buffered phase | Sponsor (on PM recommendation) | 2026-10-02 | Planning phase gate closed; Phase 3 formally started
DEC-02 | Adopt a fallback patient-identifier linking key | No clean shared identifier exists across systems | Project Manager, with Data Analytics | 2026-10-09 | Removed ambiguity blocking Phase 3 work
DEC-04 | Accept Generative AI's Week 6 safety evidence to close the Knowledge Base scope dependency | Evidence met the Quality Management Plan's criteria | Project Manager | 2026-10-27 | Assistant design work could proceed without an open governance item
DEC-05 | Apply a documented exclusion rule for the identifier's residual matching gap | Full-scale testing found a narrow gap the Week 6 sample missed | Project Manager, with Data Analytics | 2026-10-09 | DEP-002 upgraded to Validated
DEC-06 | Accept Generative AI's Week 7 retest as confirming the assistant's safety downgrade | Expanded, harder testing found and fixed only one minor issue | Project Manager | 2026-10-27 | DEP-004 upgraded to Validated
DEC-08 | Formalise the unresolved IT Lead capacity conflict as a named Sponsor decision (DEP-013) ahead of the final presentation | Two escalations without resolution; presentation must not imply deployment resourcing is settled | Project Manager | 2026-10-28 | Ensures the final presentation accurately reflects an open risk rather than a resolved one
DEC-09 | Present Week 8 output as a foundational-stage proof of concept, not a completed system | Only Phases 1–4 of 8 are complete; overclaiming would misrepresent actual progress | Project Manager | 2026-10-28 | Final presentation and all Week 8 documentation frame current status honestly

## Final Integration Record
HealthConnect Project — Final Integration Record
Consolidated record of every meaningful cross-track integration across the Experience Lab
Week | Track | Dependency | Activity | Outcome | Evidence | Status
Week 6 | Data Analytics | DEP-002 / R1 | Validated data-quality findings; adopted fallback identifier | R1 downgraded, DEP-002 mitigated | Week 6 Risk/Dependency Register, Decision Log DEC-02 | Closed
Week 6 | Generative AI | DEP-004 / R4 | Reviewed and accepted Week 6 safety/scope evidence | DEP-004 closed, R4 downgraded | Week 6 Risk/Dependency Register, Decision Log DEC-04 | Closed
Week 7 | Data Analytics | DEP-002 / R1 | Retested fallback identifier at full Phase 3 scale | DEP-002 upgraded to Validated; residual gap resolved | Week 7 Testing & Validation Record TR-01, Decision Log DEC-05 | Closed
Week 7 | Generative AI | DEP-004 / R4 | Retested assistant against expanded scenario set | DEP-004 upgraded to Validated; consistency issue resolved | Week 7 Testing & Validation Record TR-02, Decision Log DEC-06 | Closed
Week 8 | Generative AI | Final assistant capabilities & limitations | Incorporated final assistant demo scope into the final presentation structure | Final presentation coordination plan reflects confirmed assistant capabilities | Final Integration Readiness Report, Part 3 | Closed
Week 8 | Data Analytics | Final validated insights | Incorporated final business insights into the final status report and presentation narrative | Final project status report references Data Analytics' validated findings | Final Integration Readiness Report, Part 3 | Closed

## Project Readiness Assessment
HealthConnect Project — Readiness Assessment
Readiness for the final presentation/showcase of Weeks 4–8, and for the project's continued execution beyond it
Area | Readiness | Basis | Outstanding Before Presentation / Next Stage
Documentation (Charter through Week 7) | Ready | Full Initiating/Planning/Executing documentation set complete and internally consistent | None
Data quality / patient identifier | Ready | Validated at full scale (Week 7); closed | None
Generative AI assistant safety scope | Ready | Retested under harder conditions (Week 7); closed | None
No-show prediction model | Not yet ready | Testing in progress at Week 7 checkpoint; not yet finalised | Complete model testing and selection in Phase 5
ML pipeline integration | Not yet ready | Initial integration only; full build not started | Complete in Phase 5, dependent on model finalisation
IT Lead resourcing / deployment support | At risk | Escalated twice without resolution (DEP-013) | Sponsor decision required before Phase 7 planning
Overall schedule baseline | On track | No unplanned date changes since the Week 5 baseline correction | None
Presentation readiness | Ready | Final presentation structure and coordination plan complete (this package) | Confirm individual video submissions from all tracks