## Stakeholder Register
HealthConnect No-Show Reduction Project : Stakeholder Register
Project Management deliverable — Project Manager working independently of other technical delivery roles
Stakeholder | Interest in Project | Influence | Impact | Engagement Strategy | Power/Interest Quadrant
Clinic Director / Practice Manager (Project Sponsor) | High | High | High | Monthly steering committee meetings; ad hoc go/no-go reviews at each phase gate; final decision on full rollout | Manage Closely
HealthConnect Executive Committee | Medium | High | Medium | Engaged only for management-reserve or budget-escalation decisions routed by the Sponsor | Keep Satisfied
Compliance Officer (POPIA) | High | High | High | Formal sign-off at each phase gate, including the production-readiness gate; consulted on data handling design | Manage Closely
IT Lead | High | Medium | High | Weekly check-ins with the Project Manager; leads production deployment and monitoring set-up | Manage Closely
Data Engineer | High | Medium | High | Weekly check-ins; owns data preparation, integration, and pipeline build | Manage Closely
Data Scientist | High | Medium | High | Weekly check-ins; owns model development, testing, and retraining design | Manage Closely
Machine Learning Engineer | High | Low | Medium | Weekly check-ins; owns reproducibility, version control, and pipeline architecture | Keep Informed
Generative AI Developer | High | Low | Medium | Weekly check-ins; owns the patient information assistant build within approved scope | Keep Informed
Clinic Administrative & Reception Staff | Medium | Medium | High | Consulted on booking/reminder workflow; trained on dashboard and flagged-patient process ahead of the pilot | Keep Informed
Clinical Staff (Doctors, Nurses) | Medium | Medium | Medium | Consulted on scheduling impact and escalation scenarios for the assistant | Keep Informed
Patients | High | Low | High | Represented indirectly through data patterns and pilot campaign outcomes; the ultimate measure of project success | Monitor
Third-Party LLM / API Provider | Low | Medium | Medium | Monitored by the IT Lead and Generative AI Developer for availability, cost, and usage limits | Keep Satisfied

## WBS
HealthConnect No-Show Reduction Project : Work Breakdown Structure
Initiating → Planning → Executing → Closing. Dependencies shown as “# – Activity Name” — no cross-referencing required.
Code | Task Name | Description | Start Date | End Date | Owner | Notes and Dependencies
1.0 | Phase 1 — Project Initiation | Phase heading | 2026-08-31 | 2026-09-15 | —
1.1 | Confirm business problem & central question | Confirm the no-show/patient-support problem and objectives with the Sponsor. | 2026-08-31 | 2026-09-01 | Project Manager | Depends on: None (can start at project outset)
1.2 | Review data resources & confirm assumptions | Review the appointment dataset, dictionary, and knowledge base at a structural level; confirm identifier, consent, and capacity assumptions. | 2026-08-31 | 2026-09-01 | Project Manager | Depends on: None (can start at project outset)
1.3 | Develop Project Charter & obtain Sponsor sign-off | Draft and finalise the Project Charter, including scope, authority levels, and success criteria. | 2026-09-02 | 2026-09-10 | Project Manager | Depends on: 1.1 – Confirm business problem & central question; 1.2 – Review data resources & confirm assumptions
1.4 | Compile Stakeholder Register | Identify and document all project stakeholders and their engagement approach. | 2026-09-11 | 2026-09-15 | Project Manager | Depends on: 1.3 – Develop Project Charter & obtain Sponsor sign-off
1.5 | Confirm resourcing | Confirm availability of Data Engineer, Data Scientist, ML Engineer, GenAI Developer, IT Lead, Compliance Officer. | 2026-09-11 | 2026-09-15 | Project Manager | Depends on: 1.3 – Develop Project Charter & obtain Sponsor sign-off
2.0 | Phase 2 — Planning | Phase heading | 2026-09-16 | 2026-10-02 | —
2.1 | Develop Work Breakdown Structure | Decompose the project into phases, deliverables, and tasks (this table). | 2026-09-16 | 2026-09-18 | Project Manager | Depends on: 1.4 – Compile Stakeholder Register; 1.5 – Confirm resourcing
2.2 | Develop project schedule (activity durations & dependencies) | Convert the WBS into a duration- and dependency-driven activity list. | 2026-09-21 | 2026-09-23 | Project Manager | Depends on: 2.1 – Develop Work Breakdown Structure
2.3 | Build network diagram & critical path analysis | Diagram the activity network and run the CPM forward/backward pass to find the critical path. | 2026-09-24 | 2026-09-25 | Project Manager | Depends on: 2.2 – Develop project schedule (activity durations & dependencies)
2.4 | Conduct schedule risk analysis | Identify which activities have the least float and size schedule contingency around them. | 2026-09-28 | 2026-09-29 | Project Manager | Depends on: 2.3 – Build network diagram & critical path analysis
2.5 | Develop Resource Management Plan | Define roles, RACI, resource calendar, and release plan. | 2026-09-16 | 2026-09-18 | Project Manager | Depends on: 1.4 – Compile Stakeholder Register; 1.5 – Confirm resourcing
2.6 | Develop Communication Plan | Define who communicates what, to whom, how, and how often. | 2026-09-16 | 2026-09-17 | Project Manager | Depends on: 1.4 – Compile Stakeholder Register
2.7 | Develop Quality Management Plan | Define quality objectives, phase-gate evidence requirements, and QC criteria. | 2026-09-11 | 2026-09-15 | Project Manager | Depends on: 1.3 – Develop Project Charter & obtain Sponsor sign-off
2.8 | Develop cost baseline / Project Budget | Build the cost baseline and phase-by-phase budget, including the contingency reserve. | 2026-09-24 | 2026-09-28 | Project Manager | Depends on: 2.2 – Develop project schedule (activity durations & dependencies)
2.9 | Expand Risk Register & Dependency Register to full planning detail | Expand the Week 4 high-level risks/dependencies into full planning-stage detail with scores and owners. | 2026-09-30 | 2026-10-01 | Project Manager | Depends on: 2.4 – Conduct schedule risk analysis
2.10 | Planning phase gate: baseline sign-off (scope, schedule, cost) | Sponsor formally approves the scope, schedule, and cost baseline before execution begins. | 2026-10-02 | 2026-10-02 | Project Manager / Sponsor | Depends on: 2.4 – Conduct schedule risk analysis; 2.5 – Develop Resource Management Plan; 2.6 – Develop Communication Plan; 2.7 – Develop Quality Management Plan; 2.8 – Develop cost baseline / Project Budget; 2.9 – Expand Risk Register & Dependency Register to full planning detail
3.0 | Phase 3 — Analysis & Data Preparation | Phase heading | 2026-10-05 | 2026-10-14 | —
3.1 | Data quality assessment & cleaning | Assess completeness and consistency of the appointment dataset. | 2026-10-05 | 2026-10-09 | Data Engineer | Depends on: 2.10 – Planning phase gate: baseline sign-off (scope, schedule, cost)
3.2 | Exploratory data analysis & KPI definition | Explore attendance patterns; define candidate KPIs. | 2026-10-05 | 2026-10-09 | Data Scientist | Depends on: 2.10 – Planning phase gate: baseline sign-off (scope, schedule, cost)
3.3 | Confirm/construct unified patient identifier | Confirm a common identifier across scheduling and reminder records, or construct one. | 2026-10-05 | 2026-10-09 | Data Engineer | Depends on: 2.10 – Planning phase gate: baseline sign-off (scope, schedule, cost)
3.4 | Define no-show prediction problem | Define target variable and candidate input features. | 2026-10-12 | 2026-10-14 | Data Scientist | Depends on: 3.1 – Data quality assessment & cleaning; 3.2 – Exploratory data analysis & KPI definition; 3.3 – Confirm/construct unified patient identifier
4.0 | Phase 4 — Solution Design | Phase heading | 2026-10-15 | 2026-10-28 | —
4.1 | Model design & validation approach | Define modelling approach and validation methodology. | 2026-10-15 | 2026-10-20 | Data Scientist | Depends on: 3.4 – Define no-show prediction problem
4.2 | Segmentation design | Design behavioural/risk segmentation layered on prediction scores. | 2026-10-15 | 2026-10-20 | Data Scientist | Depends on: 3.4 – Define no-show prediction problem
4.3 | ML system architecture & reproducibility design | Design the high-level, reproducible ML system architecture. | 2026-10-21 | 2026-10-27 | ML Engineer | Depends on: 4.1 – Model design & validation approach; 4.2 – Segmentation design
4.4 | GenAI assistant scope & safety boundaries | Define assistant use cases, out-of-scope requests, and safety/escalation design. | 2026-10-21 | 2026-10-27 | Generative AI Developer | Depends on: 4.1 – Model design & validation approach; 4.2 – Segmentation design
4.5 | Dashboard/report design | Design the at-risk patient dashboard for clinic staff. | 2026-10-21 | 2026-10-27 | Data Engineer | Depends on: 4.1 – Model design & validation approach; 4.2 – Segmentation design
4.6 | Phase gate: design review & Sponsor go/no-go | Present design outputs to the Sponsor for approval to proceed. | 2026-10-28 | 2026-10-28 | Project Manager / Sponsor | Depends on: 4.3 – ML system architecture & reproducibility design; 4.4 – GenAI assistant scope & safety boundaries; 4.5 – Dashboard/report design
5.0 | Phase 5 — Model & Assistant Development | Phase heading | 2026-10-29 | 2027-02-04 | —
5.1 | Build & iteratively test no-show prediction model | Iterative build-test cycles for the prediction model. | 2026-10-29 | 2027-01-20 | Data Scientist | Depends on: 4.6 – Phase gate: design review & Sponsor go/no-go
5.2 | Build data integration / pipeline | Build the data preparation and integration pipeline. | 2026-10-29 | 2026-11-25 | Data Engineer | Depends on: 4.6 – Phase gate: design review & Sponsor go/no-go
5.3 | Build reproducible ML pipeline & version control | Implement pipeline versioning and reproducibility structure. | 2026-11-26 | 2027-01-20 | ML Engineer | Depends on: 5.2 – Build data integration / pipeline
5.4 | Build GenAI assistant prototype | Build the patient information assistant within the approved Knowledge Base scope. | 2026-10-29 | 2027-02-03 | Generative AI Developer | Depends on: 4.6 – Phase gate: design review & Sponsor go/no-go
5.5 | Build dashboard/reporting | Build the at-risk patient dashboard for clinic staff. | 2026-11-26 | 2027-01-13 | Data Engineer | Depends on: 5.2 – Build data integration / pipeline
5.6 | Mid-development integration checkpoint | Confirm model, pipeline, assistant, and dashboard integrate as designed. | 2027-02-04 | 2027-02-04 | Project Manager | Depends on: 5.1 – Build & iteratively test no-show prediction model; 5.3 – Build reproducible ML pipeline & version control; 5.4 – Build GenAI assistant prototype; 5.5 – Build dashboard/reporting
6.0 | Phase 6 — Pilot Campaign | Phase heading | 2027-02-05 | 2027-02-19 | —
6.1 | Validate segments with clinic staff | Clinic staff review and validate risk segments. | 2027-02-05 | 2027-02-08 | Clinic Admin & Clinical Staff | Depends on: 5.6 – Mid-development integration checkpoint
6.2 | Train staff on dashboard & flagged-patient process | Train administrative and clinical staff on the dashboard and intervention process. | 2027-02-09 | 2027-02-11 | Project Manager | Depends on: 6.1 – Validate segments with clinic staff
6.3 | Run pilot reminder/retention campaign | Execute the pilot campaign on flagged at-risk patients. | 2027-02-12 | 2027-02-18 | Clinic Admin & Clinical Staff | Depends on: 6.2 – Train staff on dashboard & flagged-patient process
6.4 | Measure pilot results vs. control group | Compare no-show rate of the flagged/treated group against a control group. | 2027-02-19 | 2027-02-19 | Data Scientist | Depends on: 6.3 – Run pilot reminder/retention campaign
7.0 | Phase 7 — Testing, Deployment & Monitoring | Phase heading | 2027-02-22 | 2027-03-10 | —
7.1 | Model validation against test data & KPI targets | Validate model accuracy against the held-out test dataset and the 75% target. | 2027-02-22 | 2027-02-24 | Data Scientist | Depends on: 6.4 – Measure pilot results vs. control group
7.2 | Assistant safety & scope testing | Test the assistant's adherence to safety boundaries and escalation rules. | 2027-02-22 | 2027-02-24 | Generative AI Developer | Depends on: 6.4 – Measure pilot results vs. control group
7.3 | Production deployment | Deploy the model, dashboard, and assistant to production. | 2027-02-25 | 2027-03-03 | IT Lead | Depends on: 7.1 – Model validation against test data & KPI targets; 7.2 – Assistant safety & scope testing
7.4 | Establish monitoring & retraining schedule | Stand up the ongoing monitoring process and define the retraining schedule. | 2027-03-04 | 2027-03-10 | Data Scientist / ML Engineer | Depends on: 7.3 – Production deployment
8.0 | Phase 8 — Operational Handover & Closure | Phase heading | 2027-03-11 | 2027-03-17 | —
8.1 | Train internal IT/Data team | Train HealthConnect's internal IT/Data team on monitoring and retraining. | 2027-03-11 | 2027-03-15 | Project Manager / Data Scientist | Depends on: 7.4 – Establish monitoring & retraining schedule
8.2 | Final presentation & documentation handover | Present consolidated outcomes and hand over documentation. | 2027-03-16 | 2027-03-16 | Project Manager | Depends on: 8.1 – Train internal IT/Data team
8.3 | Project closure & lessons learned | Formal closure, retrospective, and lessons-learned capture. | 2027-03-17 | 2027-03-17 | Project Manager | Milestone. Depends on: 8.2 – Final presentation & documentation handover
9.0 | Phase 9 — Project Management (continuous) | Phase heading | 2026-08-31 | 2027-03-17 | —
9.1 | Weekly status tracking & risk/dependency monitoring | Track task progress; update the risk and dependency registers. | 2026-08-31 | 2027-03-17 | Project Manager | Runs throughout; no single predecessor
9.2 | Budget tracking & contingency management | Track budget vs actual; log any contingency draws. | 2026-08-31 | 2027-03-17 | Project Manager | Runs throughout; no single predecessor
9.3 | Steering committee reporting | Prepare and present monthly steering committee updates. | 2026-08-31 | 2027-03-17 | Project Manager | Runs throughout; monthly cadence

## Risk Register
HealthConnect No-Show Reduction Project : Risk Register
Risk Score = Likelihood value × Impact value (see scale, cols J:K)
ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner | Scale
R1 | Data quality issues in the appointment dataset (missing, inconsistent, or unclear fields) | Data | Medium | High | 6 | Early data quality assessment (WBS 2.1); document assumptions and cleaning steps before modelling | Data Engineer | Level | Value
R2 | No-show prediction model accuracy falls below the 75% target | Model | Medium | High | 6 | Iterative build-test cycles (WBS 4.1); feature engineering review if early accuracy lags | Data Scientist | Low | 1
R3 | Low staff adoption of at-risk patient flags and reminder recommendations | Adoption | Medium | Medium | 4 | Early staff involvement in segment validation (WBS 5.1) and structured training (WBS 5.2) | Project Manager | Medium | 2
R4 | Generative AI assistant produces out-of-scope or unsafe responses (e.g., clinical advice) | Safety / Compliance | Medium | High | 6 | Strict Knowledge-Base-only design (WBS 3.4); dedicated safety and scope testing (WBS 6.2) | Generative AI Developer | High | 3
R5 | Insufficient internal capacity at HealthConnect to sustain monitoring and retraining after handover | Operational | Medium | High | 6 | Confirm internal team availability early (DEP-008); structured handover training (WBS 7.1) | Project Manager
R6 | Data privacy / POPIA compliance exposure given health-related patient data | Compliance | Medium | High | 6 | Compliance Officer sign-off at each phase gate; confirm consent status early (DEP-003) | Compliance Officer
R7 | Schedule pressure from the December office closure falling within the project timeline | Schedule | High | Medium | 6 | December fully excluded from the active 20-week schedule; work resumes in January with buffer | Project Manager
R8 | Dependency on third-party LLM/API availability, rate limits, or cost for the assistant | Technical / Vendor | Low | Medium | 2 | Early API access testing (WBS 4.4); fallback/offline model option identified | IT Lead
R9 | Scope creep beyond the agreed prototype/pilot boundary into full production rollout without sign-off | Scope | Low | High | 3 | Reinforce Scope Statement; Sponsor sign-off required through change control for any scope change | Project Manager
R10 | Budget overrun beyond the approved contingency due to unforeseen integration complexity | Financial | Low | Medium | 2 | Weekly budget tracking (WBS 8.2); contingency draws logged and approved per the authority matrix | Project Manager

## Communication Plan
HealthConnect No-Show Reduction Project : Communication Plan
Owned and originated by the Project Manager unless noted otherwise
Team Members | Information | Frequency | Method | Owner
Clinic Director / Practice Manager (Sponsor) | Progress vs. plan, budget-vs-actual, risk register status, decisions required | Weekly written update; monthly meeting | Status report (email) + Steering Committee meeting | Project Manager
Project Steering Committee | Milestone/phase-gate outcomes, go/no-go decisions, pilot results | Monthly, plus ad hoc at each phase gate | Steering Committee meeting | Project Manager
Compliance Officer | POPIA compliance status, data handling review outcomes | At each phase gate and as needed | Formal review meeting / document sign-off | Project Manager
IT Lead | System access, technical dependencies, deployment readiness | Weekly; increasing to twice-weekly during Weeks 18–19 (deployment) | Check-in meeting + email | Project Manager
Data Engineer / Data Scientist / ML Engineer / Generative AI Developer | Task progress, blockers, technical decisions | Weekly | Check-in meeting + project tracking tool | Project Manager
Clinic Administrative & Clinical Staff | Segment validation, dashboard training, pilot campaign coordination | As needed, concentrated in Weeks 15–17 | Training session + email updates | Project Manager
HealthConnect Internal IT/Data Team | Handover training, monitoring and retraining process | Concentrated in Week 20 (handover) | Handover workshop + written documentation | Project Manager
Finance / Executive Committee | Budget-vs-actual reporting | Monthly | Budget report (Excel) | Project Manager

## Dependency Register
HealthConnect No-Show Reduction Project : Dependency Register
Tracked separately from the Risk Register
Dependency ID | Dependency / Description | Dependent Activity/Task | Dependency Type | Source / Owner | Required By | Status | Impact if Delayed | Criticality | Mitigation / Action | Responsible Person | Notes
DEP-001 | Confirmed access to the HealthConnect Appointment Dataset, usable for analysis and modelling | 2.1 Data quality assessment & cleaning | Internal / Data | IT Lead | 2026-09-11 | In Progress | Data preparation and modelling timeline slips | High | Escalate to Sponsor for prioritised IT access | Data Engineer | Dataset provided as a single fictional/anonymised file
DEP-002 | A common (or derivable) patient identifier confirmed across scheduling and reminder records | 2.3 Confirm/construct unified patient identifier | Technical | IT Lead | 2026-09-18 | Not Started | Data integration requires rework | Critical | Build a matching/linking key as a fallback if no shared identifier exists | Data Engineer
DEP-003 | POPIA consent status confirmed for the appointment data used in the project | 1.2 Review data resources & confirm assumptions | Regulatory / Compliance | Compliance Officer | 2026-09-04 | In Progress | Project pauses pending compliance clearance | Critical | Request early written confirmation from Compliance | Project Manager
DEP-004 | Finalised, Sponsor-approved Clinic Knowledge Base scope for the patient information assistant | 3.4 GenAI assistant scope & safety boundaries | Internal / Content | Clinic Administration | 2026-10-09 | Not Started | Assistant scope and safety boundaries remain undefined | High | Draft an interim scope for Sponsor approval if the final Knowledge Base is delayed | Project Manager
DEP-005 | Administrative and clinical staff availability for segment validation and pilot execution | 5.1 Validate segments with clinic staff | Resource | Clinic Administrative & Clinical Staff | 2027-01-19 | Not Started | Pilot campaign delayed or under-resourced | Medium | Confirm staff resourcing at the Phase 3 gate | Project Manager
DEP-006 | Third-party LLM/API access, licensing terms, and usage limits confirmed | 4.4 Build GenAI assistant prototype | External / Vendor | IT Lead / LLM Provider | 2026-10-12 | Not Started | Assistant build blocked or delayed | Medium | Identify a fallback or offline model option | IT Lead
DEP-007 | Production environment / hosting readiness for the model, dashboard, and assistant | 6.3 Production deployment | Technical | IT Lead | 2027-02-04 | Not Started | Deployment slips past the planned date | High | Confirm environment readiness early in Phase 4 | IT Lead
DEP-008 | HealthConnect internal IT/Data team nominated and available for handover training | 7.1 Train internal IT/Data team | Resource / Internal | Clinic Management | 2027-02-15 | Not Started | Handover delayed; consultant support required beyond Week 20 | High | Confirm nominated staff at the Phase 6 gate | Project Manager

## Detailed Timeline
HealthConnect No-Show Reduction Project : Detailed Timeline
31 Aug 2026 – 2027-03-17 (Initiating → Planning → Executing → Closing; December fully excluded). Each phase lists its key activities and closes with a milestone.
Major Phase | Key Activity | Milestone | Start Date | End Date | Depends On
Phase 1 : Project Initiation (2026-08-31 to 2026-09-15) | • 1.1 Confirm business problem & central question |  | 2026-08-31 | 2026-09-01 | :
| • 1.2 Review data resources & confirm assumptions |  | 2026-08-31 | 2026-09-01 | :
| • 1.3 Develop Project Charter & obtain Sponsor sign-off |  | 2026-09-02 | 2026-09-10 | 1.1; 1.2
| • 1.4 Compile Stakeholder Register |  | 2026-09-11 | 2026-09-15 | 1.3
| • 1.5 Confirm resourcing |  | 2026-09-11 | 2026-09-15 | 1.3
| Milestone | Project Charter approved by Sponsor | 2026-09-15 | 2026-09-15
Phase 2 : Planning (2026-09-16 to 2026-10-02) | • 2.1 Develop Work Breakdown Structure |  | 2026-09-16 | 2026-09-18 | 1.4; 1.5
| • 2.2 Develop project schedule (activity durations & dependencies) |  | 2026-09-21 | 2026-09-23 | 2.1
| • 2.3 Build network diagram & critical path analysis |  | 2026-09-24 | 2026-09-25 | 2.2
| • 2.4 Conduct schedule risk analysis |  | 2026-09-28 | 2026-09-29 | 2.3
| • 2.5 Develop Resource Management Plan |  | 2026-09-16 | 2026-09-18 | 1.4; 1.5
| • 2.6 Develop Communication Plan |  | 2026-09-16 | 2026-09-17 | 1.4
| • 2.7 Develop Quality Management Plan |  | 2026-09-11 | 2026-09-15 | 1.3
| • 2.8 Develop cost baseline / Project Budget |  | 2026-09-24 | 2026-09-28 | 2.2
| • 2.9 Expand Risk Register & Dependency Register to full planning detail |  | 2026-09-30 | 2026-10-01 | 2.4
| • 2.10 Planning phase gate: baseline sign-off (scope, schedule, cost) |  | 2026-10-02 | 2026-10-02 | 2.4; 2.5; 2.6; 2.7; 2.8; 2.9
| Milestone | Planning phase gate: baseline sign-off (scope, schedule, cost) | 2026-10-02 | 2026-10-02
Phase 3 : Analysis & Data Preparation (2026-10-05 to 2026-10-14) | • 3.1 Data quality assessment & cleaning |  | 2026-10-05 | 2026-10-09 | 2.10
| • 3.2 Exploratory data analysis & KPI definition |  | 2026-10-05 | 2026-10-09 | 2.10
| • 3.3 Confirm/construct unified patient identifier |  | 2026-10-05 | 2026-10-09 | 2.10
| • 3.4 Define no-show prediction problem |  | 2026-10-12 | 2026-10-14 | 3.1; 3.2; 3.3
| Milestone | No-show prediction problem formally defined | 2026-10-14 | 2026-10-14
Phase 4 : Solution Design (2026-10-15 to 2026-10-28) | • 4.1 Model design & validation approach |  | 2026-10-15 | 2026-10-20 | 3.4
| • 4.2 Segmentation design |  | 2026-10-15 | 2026-10-20 | 3.4
| • 4.3 ML system architecture & reproducibility design |  | 2026-10-21 | 2026-10-27 | 4.1; 4.2
| • 4.4 GenAI assistant scope & safety boundaries |  | 2026-10-21 | 2026-10-27 | 4.1; 4.2
| • 4.5 Dashboard/report design |  | 2026-10-21 | 2026-10-27 | 4.1; 4.2
| • 4.6 Phase gate: design review & Sponsor go/no-go |  | 2026-10-28 | 2026-10-28 | 4.3; 4.4; 4.5
| Milestone | Design approved at Phase Gate (Sponsor go/no-go) | 2026-10-28 | 2026-10-28
Phase 5 : Model & Assistant Development (2026-10-29 to 2027-02-04) | • 5.1 Build & iteratively test no-show prediction model |  | 2026-10-29 | 2027-01-20 | 4.6
| • 5.2 Build data integration / pipeline |  | 2026-10-29 | 2026-11-25 | 4.6
| • 5.3 Build reproducible ML pipeline & version control |  | 2026-11-26 | 2027-01-20 | 5.2
| • 5.4 Build GenAI assistant prototype |  | 2026-10-29 | 2027-02-03 | 4.6
| • 5.5 Build dashboard/reporting |  | 2026-11-26 | 2027-01-13 | 5.2
| • 5.6 Mid-development integration checkpoint |  | 2027-02-04 | 2027-02-04 | 5.1; 5.3; 5.4; 5.5
| Milestone | Mid-development integration checkpoint | 2027-02-04 | 2027-02-04
Phase 6 : Pilot Campaign (2027-02-05 to 2027-02-19) | • 6.1 Validate segments with clinic staff |  | 2027-02-05 | 2027-02-08 | 5.6
| • 6.2 Train staff on dashboard & flagged-patient process |  | 2027-02-09 | 2027-02-11 | 6.1
| • 6.3 Run pilot reminder/retention campaign |  | 2027-02-12 | 2027-02-18 | 6.2
| • 6.4 Measure pilot results vs. control group |  | 2027-02-19 | 2027-02-19 | 6.3
| Milestone | Pilot results measured against control group | 2027-02-19 | 2027-02-19
Phase 7 : Testing, Deployment & Monitoring (2027-02-22 to 2027-03-10) | • 7.1 Model validation against test data & KPI targets |  | 2027-02-22 | 2027-02-24 | 6.4
| • 7.2 Assistant safety & scope testing |  | 2027-02-22 | 2027-02-24 | 6.4
| • 7.3 Production deployment |  | 2027-02-25 | 2027-03-03 | 7.1; 7.2
| • 7.4 Establish monitoring & retraining schedule |  | 2027-03-04 | 2027-03-10 | 7.3
| Milestone | Model and assistant live in production | 2027-03-10 | 2027-03-10
Phase 8 : Operational Handover & Closure (2027-03-11 to 2027-03-17) | • 8.1 Train internal IT/Data team |  | 2027-03-11 | 2027-03-15 | 7.4
| • 8.2 Final presentation & documentation handover |  | 2027-03-16 | 2027-03-16 | 8.1
| • 8.3 Project closure & lessons learned |  | 2027-03-17 | 2027-03-17 | 8.2
| Milestone | Operational handover complete; project closed | 2027-03-17 | 2027-03-17